## EPC Report pemasangan-BSS
No | EPC Name | Charging Type | Project Status | PLN Status | Project / Location Name | Address | Google Map URL | Province | City | BD PIC | SS WO number | SS Date (Schedule w/ Landlord) | SS Report Submission Date | Cable Length (kWH to Panel) | Cable Length (Panel to Charger) | Cable Pulling Type | Power (Daya kVA) | SSR URL (Report & Quotation) | Parking Slot | Charging Station Count | Setup Approval Date | Cons WO number | Cons Actual Start Date | Cons Actual Done Date | NIDI SLO Date Acquired | BPUJL Date Acquired | NIDI SLO, BPUJL URL | SIK URL | Type Rate | kWh Meter PLN Installation Date | Machine SN (SERIAL NUMBER) | ID PELANGGAN (ID PLN) | NOMOR SIMCARD | Go LIVE Date (by pass) | Go LIVE Date (PLN) | Latest Remark / Notes | Tanggal Pengajuan Invoice | DP 35% Date | Tanggal Pengajuan Invoice | 60% Payment Date | Tanggal Pengajuan Invoice | 5% Payment Date | Invoice URL
1 | SIGMATEC | BSS | Done Cons | DONE KWH | Cibungbulang [CGG] | JL. RAYA CIBUNGBULANG RT. 02/05 | https://www.google.com/maps?q=-6.574755,106.661308 | West Java | Bogor | Farizan | (no WO survey) | - | - |  |  | New Power | 7.7kVA |  |  | 1 |  | VGID-WO/BD/2026/I/0319 | 2026-01-30 | 2026-02-03 | 2026-02-05 | 2026-02-24 |  |  |  | 2026-03-02 | 254941002381 | 538516451141 |  |  |  | PLN ON | 2026-03-17
2 | SIGMATEC | BSS | Done Cons | DONE KWH | Sukahati [SHT] | JL. KSR DADI KUSMAYADI NO.6 RT. 01/09 | https://www.google.com/maps?q=-6.478857,106.818094 | West Java | Bogor | Farizan | (no WO survey) | - | - |  |  | New Power | 7.7kVA |  |  | 1 |  | VGID-WO/BD/2026/I/0319 | 2026-01-30 | 2026-02-04 | 2026-02-05 | 2026-02-24 |  |  |  | 2026-03-02 | 255041000606 | 538516776900 |  |  |  | PLN ON | 2026-03-17
3 | SIGMATEC | BSS | Drop | NOT YET REGISTER | Metland Cileungsi [MCI] | JL. BOULEVARD METLAND CILEUNGSI BLOK DE 1 NO.15 RT.03/25 | https://www.google.com/maps?q=-6.390100,106.986679 | West Java | Bogor | Farizan | (no WO survey) | - | - |  |  | New Power | 7.7kVA |  |  |  |  | VGID-WO/BD/2026/I/0319 | - | - | 2026-02-05 | - |  |  |  | - | [5 empty] | - | -
4 | SIGMATEC | BSS | Done Cons | DONE KWH | Cilebut [CBT] | RUKO PERUM PESONA CILEBUT JL. PENDIDIKAN BLOK B.01 NO.1&3 RT. 05/14 | https://www.google.com/maps?q=-6.530700,106.799443 | West Java | Bogor | Farizan | (no WO survey) | - | - |  |  | New Power | 7.7kVA |  |  | 1 |  | VGID-WO/BD/2026/I/0319 | 2026-01-30 | 2026-02-04 | 2026-02-05 | 2026-02-23 |  |  |  | 2026-04-14 | 254941002430 | 538415054541 |  |  |  | PLN ON | 2026-03-17
5 | SIGMATEC | BSS | Done Cons | DONE KWH | Shopping Street [SST] | JL. CITRA INDAH RUKO SHOPPING STREET BLOK SS 02 NO.21&23 RT.08/09 | https://www.google.com/maps?q=-6.452269,107.041228 | West Java | Bogor | Farizan | (no WO survey) | - | - |  |  | New Power | 7.7kVA |  |  | 1 |  | VGID-WO/BD/2026/I/0319 | 2026-01-31 | 2026-02-05 | 2026-02-05 | 2026-02-24 |  |  |  | 2026-03-03 | 255041000840 | 538671620282 |  |  |  | PLN ON | 2026-03-17
6 | SIGMATEC | BSS | Done Cons | DONE KWH | Dago Parung Panjang [DPG] | JL. RAYA DAGO RT.02/02 | https://www.google.com/maps?q=-6.350825,106.576950 | West Java | Bogor | Farizan | (no WO survey) | - | - |  |  | New Power | 7.7kVA |  |  | 1 |  | VGID-WO/BD/2026/I/0319 | 2026-01-31 | 2026-02-03 | 2026-02-05 | 2026-02-23 |  |  |  | 2026-04-25 | 255041000534 | 538531777640 |  |  |  | PLN ON | 2026-03-17
7 | SIGMATEC | BSS | Done Cons | DONE KWH | Villa Nusa Indah [VNI] | JL. RAYA VILLA NUSA INDAH BLOK S.6/02 RT 02/22 | https://www.google.com/maps?q=-6.312784,106.972740 | West Java | Bogor | Farizan | (no WO survey) | - | - |  |  | New Power | 7.7kVA |  |  | 1 |  | VGID-WO/BD/2026/I/0319 | 2026-01-31 | 2026-02-04 | 2026-02-05 | 2026-02-23 |  |  |  | 2026-03-05 | 255041000777 | 538657784962 |  |  |  | PLN ON | 2026-03-17
8 | SIGMATEC | BSS | Done Cons | DONE KWH | Sentraland [SRD] | JL. SENTRALAND BOULEVARD BLOK I NO.17,18,19 | https://www.google.com/maps?q=-6.352326,106.568107 | West Java | Bogor | Farizan | (no WO survey) | - | - |  |  | New Power | 7.7kVA |  |  | 1 |  | VGID-WO/BD/2026/I/0319 | 2026-01-31 | 2026-02-03 | 2026-02-06 | 2026-02-23 |  |  |  | 2026-04-25 | 254941002149 | 538531777632 |  |  |  | PLN ON | 2026-03-17
9 | SIGMATEC | BSS | Done Cons | DONE KWH | Bukit Dago [BDO] | JL. PENDIDIKAN RUKO BUKIT DAGO BLOK AA3 NO.1&2 RT.07/14 | https://www.google.com/maps?q=-6.363273,106.700719 | West Java | Bogor | Farizan | (no WO survey) | - | - |  |  | New Power | 7.7kVA |  |  | 1 |  | VGID-WO/BD/2026/I/0319 | 2026-01-30 | 2026-02-05 | 2026-02-06 | 2026-02-23 |  |  |  | 2026-02-25 | 254941002155 | 538734505336 |  |  |  | PLN ON | 2026-03-17
10 | SIGMATEC | BSS | Done Cons | DONE KWH | Tugu Macan [TMN] | JL. KP. BAMBON NO.89 RT.01/06 | https://www.google.com/maps?q=-6.448216,106.785810 | West Java | Bogor | Farizan | (no WO survey) | - | - |  |  | New Power | 7.7kVA |  |  | 1 |  | VGID-WO/BD/2026/I/0319 | 2026-01-30 | 2026-02-04 | 2026-02-07 | 2026-02-23 |  |  |  | 2026-02-25 | 255041000899 | 538751372823 |  |  |  | PLN ON | 2026-03-17
11 | SIGMATEC | BSS | Done Cons | DONE KWH | Kapten Yusuf [KYF] | JL. KAPTEN YUSUF RT.06/05 | https://www.google.com/maps?q=-6.615937,106.785228 | West Java | Bogor | Farizan | (no WO survey) | - | - |  |  | New Power | 7.7kVA |  |  | 1 |  | VGID-WO/BD/2026/I/0319 | 2026-01-30 | 2026-02-03 | 2026-02-07 | 2026-02-23 |  |  |  | 2026-04-21 | 255041000527 | 538316294705 |  |  |  | PLN ON | 2026-03-17
12 | SIGMATEC | BSS | Done Cons | DONE KWH | Raya Ciomas [RCS] | JL. RAYA CIOMAS RT.03/010 | https://www.google.com/maps?q=-6.602858,106.766816 | West Java | Bogor | Farizan | (no WO survey) | - | - |  |  | New Power | 7.7kVA |  |  | 1 |  | VGID-WO/BD/2026/I/0319 | 2026-01-30 | 2026-02-03 | 2026-02-07 | 2026-02-23 |  |  |  | 2026-04-21 | 255041000811 | 538316294691 |  |  |  | PLN ON | 2026-03-17
13 | SIGMATEC | BSS | Done Cons | DONE KWH | Tentara Pelajar [TPR] | JL. TENTARA PELAJAR RT.01/16 | https://www.google.com/maps?q=-6.5715696,106.7877367 | West Java | Bogor | Farizan | (no WO survey) | - | - |  |  | New Power | 7.7kVA |  |  | 1 |  | VGID-WO/BD/2026/I/0319 | 2026-01-30 | 2026-02-04 | 2026-02-07 | 2026-02-24 |  |  |  | 2026-04-27 | 254941002157 | 538415054558 |  |  |  | PLN ON | 2026-03-17
14 | SIGMATEC | BSS | On Cons | WAITING KWH | Kantor Pos KC Cilacap | Jl. A Yani No. 32 Cilacap 53212 | https://maps.app.goo.gl /TzRUDftXHoxY3jr86 | Central Java | Cilacap | Ditto | (no WO survey) | 2026-03-31 | 2026-03-31 |  |  | New Power | 7.7kVA |  |  | 1 | 2026-02-28 | VGID-WO/BD/2026/II/0430 |  |  | 2026-03-02 | no reg 5250111084265 | [9 empty] | menunggu BA survey dari pihak Kantor Pos ke V-Green, info per 8 Apr | 2026-04-06
15 | SIGMATEC | BSS | On Cons | WAITING KWH | Kantor Pos KC Banjarnegara | Jl. Pemuda No. 72 | https://maps.app.goo.gl /nHo1H9wRtGMdYBqn8 | Central Java | Banjarnegara | Ditto | (no WO survey) | 2026-03-06 | 2026-03-31 |  |  | New Power | 7.7kVA |  |  | 1 | 2026-02-28 | VGID-WO/BD/2026/II/0430 |  |  | 2026-03-02 | no reg 5220411205003 | [9 empty] | menunggu BA survey dari pihak Kantor Pos ke V-Green, info per 8 Apr | 2026-04-06
16 | SIGMATEC | BSS | Done Cons | DONE KWH | Kantor Pos KC Kebumen | Jl. Pahlawan No. 169 | https://maps.app.goo.gl /vBDQ2mBvQbFtuGcE9 | Central Java | Kebumen | Ditto | (no WO survey) | 2026-03-07 | 2026-03-31 |  |  | New Power | 7.7kVA |  |  | 1 | 2026-02-28 | VGID-WO/BD/2026/II/0430 | 2026-04-25 | 2026-04-25 | 2026-03-02 | no reg 5250411178682 |  |  |  | 2026-04-25 |  | 525043434514 |  |  |  |  | 2026-04-06
17 | SIGMATEC | BSS | On Cons | NOT YET REGISTER | Kantor Pos KCU Solo | Jl. Jend. Sudirman No. 8 Solo 57111 | https://maps.app.goo.gl /y8XS5cuttThYds9L7 | Central Java | Solo | Ditto | (no WO survey) | 2026-03-02 | 2026-03-31 |  |  | New Power | 7.7kVA |  |  | 1 | 2026-02-28 | VGID-WO/BD/2026/II/0430 |  |  | 2026-03-11 | [10 empty] | menunggu BA survey dari pihak Kantor Pos ke V-Green, info per 8 Apr | 2026-04-06
18 | SIGMATEC | BSS | On Cons | NOT YET REGISTER | Kantor Pos KC Boyolali | Jl. Pandanaran No. 64 Boyolali | https://maps.app.goo.gl /P3agjbr5j36Ls2tJ7 | Central Java | Boyolali | Ditto | (no WO survey) | 2026-03-03 | 2026-04-01 |  |  | New Power | 7.7kVA |  |  | 1 | 2026-02-28 | VGID-WO/BD/2026/II/0430 |  |  | 2026-03-11 | [10 empty] | menunggu BA survey dari pihak Kantor Pos ke V-Green, info per 8 Apr | 2026-04-06
19 | SIGMATEC | BSS | On Cons | NOT YET REGISTER | Kantor Pos KC Klaten | Jl. Pemuda No. 199 Klaten 57411 | https://maps.app.goo.gl /zHGEpggPp8w1Axg38 | Central Java | Klaten | Ditto | (no WO survey) | 2026-03-26 | 2026-03-31 |  |  | New Power | 7.7kVA |  |  | 1 | 2026-02-28 | VGID-WO/BD/2026/II/0430 |  |  | 2026-03-11 | [10 empty] | menunggu BA survey dari pihak Kantor Pos ke V-Green, info per 8 Apr | 2026-04-06
20 | SIGMATEC | BSS | On Cons | NOT YET REGISTER | Kantor Pos KC Sukoharjo | Jl. Wandyopranoto No. 12 | https://maps.app.goo.gl /qG2uMjT71uHWAohY8 | Central Java | Sukoharjo | Ditto | (no WO survey) | 2026-03-06 | 2026-03-31 |  |  | New Power | 7.7kVA |  |  | 1 | 2026-02-28 | VGID-WO/BD/2026/II/0430 |  |  | 2026-03-11 | [10 empty] | menunggu BA survey dari pihak Kantor Pos ke V-Green, info per 8 Apr | 2026-04-06
21 | SIGMATEC | BSS | On Cons | NOT YET REGISTER | Kantor Pos KC Wonogiri | Jl. Ahmad Yani No. 168 Wonogiri | https://maps.app.goo.gl /eyTGCQagzA4mpv4m8 | Central Java | Wonogiri | Ditto | (no WO survey) | 2026-03-06 | 2026-03-31 |  |  | New Power | 7.7kVA |  |  | 1 | 2026-02-28 | VGID-WO/BD/2026/II/0430 |  |  | 2026-03-11 | [10 empty] | menunggu BA survey dari pihak Kantor Pos ke V-Green, info per 8 Apr | 2026-04-06
22 | SIGMATEC | BSS | SS Done | NOT YET REGISTER | Kantor Pos KpcLK Jumapolo 57783 | Jl Raya Jumapolo | https://maps.app.goo.gl/b67uJdH2HF1eTQeTA | Central Java | Jumapolo | Samiadji Huda | VGID-WO/BD/2026/II/0546 | 2026-03-06 | 2026-04-01 |  |  | New Power | 7.7kVA |  |  | 1 | [15 empty] | menunggu BA survey dari pihak Kantor Pos ke V-Green, info per 8 Apr
23 | SIGMATEC | BSS | SS Done | NOT YET REGISTER | Kantor Pos KpcLK Matesih 57781 | Jl Tentara Pelajar Joko Songo | https://maps.app.goo.gl/BfLnzwV1wp485MVQ8 | Central Java | Matesih | Samiadji Huda | VGID-WO/BD/2026/II/0546 | 2026-03-06 | 2026-04-01 |  |  | New Power | 7.7kVA |  |  | 1 | [15 empty] | menunggu BA survey dari pihak Kantor Pos ke V-Green, info per 8 Apr
24 | SIGMATEC | BSS | SS Done | NOT YET REGISTER | Kantor Pos Kpclk Tawangmangu | Jl Lawu no. 08 | https://maps.app.goo.gl/SesBxpotHib8kLfn6 | Central Java | Tawangmangu | Samiadji Huda | VGID-WO/BD/2026/II/0546 | 2026-03-06 | 2026-03-31 |  |  | New Power | 7.7kVA |  |  | 1 | [15 empty] | menunggu BA survey dari pihak Kantor Pos ke V-Green, info per 8 Apr
25 | SIGMATEC | BSS | Site Survey | NOT YET REGISTER | Kantor Pos KpcLK Prambanan 57454 | DK Prambodoharjo | https://maps.app.goo.gl/WDLHdGD5RBm4JQv97 | Central Java | Prambanan | Samiadji Huda | VGID-WO/BD/2026/II/0546 |  |  |  |  | New Power | 7.7kVA |  |  | 1 | [15 empty] | menunggu konfirmasi dari regional
26 | SIGMATEC | BSS | Drop | NOT YET REGISTER | Kantor Pos KpcLK Kajen 51161 | Jl Raya Kajen - Karanganyar no. 347 | https://maps.app.goo.gl/r6R8hBsEUi5sddak7 | Central Java | Kajen | Samiadji Huda | VGID-WO/BD/2026/II/0546 |  |  |  |  | New Power | 7.7kVA |  |  | 1 | [15 empty] | Lokasi tidak sesuai titik, terlalu jauh
27 | SIGMATEC | BSS | SS Done | NOT YET REGISTER | Kantor Pos KpcLK Bukateja 53382 | Jl Raya Bukateja | https://maps.app.goo.gl/9zBj8rEEE5TUCAMs8 | Central Java | Bukateja | Samiadji Huda | VGID-WO/BD/2026/II/0546 | 2026-03-06 | 2026-03-31 |  |  | New Power | 7.7kVA |  |  | 1 | [15 empty] | menunggu BA survey dari pihak Kantor Pos ke V-Green, info per 8 Apr
28 | SIGMATEC | BSS | SS Done | NOT YET REGISTER | Kantor Pos Kpclk Annex Banyumas 53192 | Jl Pramuka no. 18 | https://maps.app.goo.gl/5yZyfrgze9SMFQiE6 | Central Java | Banyumas | Samiadji Huda | VGID-WO/BD/2026/II/0546 | 2026-03-06 | 2026-03-31 |  |  | New Power | 7.7kVA |  |  | 1 | [15 empty] | menunggu BA survey dari pihak Kantor Pos ke V-Green, info per 8 Apr
29 | SIGMATEC | BSS | SS Done | NOT YET REGISTER | Kantor Pos Kpclk Annex Jatilawang | Jl Raya Jatilawang no. 10 | https://maps.app.goo.gl/sYVmZVo3ZqHfVYabA | Central Java | Jatilawang | Samiadji Huda | VGID-WO/BD/2026/II/0546 | 2026-03-06 | 2026-03-31 |  |  | New Power | 7.7kVA |  |  | 1 | [15 empty] | menunggu BA survey dari pihak Kantor Pos ke V-Green, info per 8 Apr
30 | SIGMATEC | BSS | SS Done | NOT YET REGISTER | Kantor Pos Kpclk Annex Ajibarang | Jl Raya Ajibarang no. 3 | https://maps.app.goo.gl/f9o4qFu1iK7eN4697 | Central Java | Ajibarang | Samiadji Huda | VGID-WO/BD/2026/II/0546 | 2026-03-06 | 2026-03-31 |  |  | New Power | 7.7kVA |  |  | 1 | [15 empty] | menunggu BA survey dari pihak Kantor Pos ke V-Green, info per 8 Apr
31 | SIGMATEC | BSS | SS Done | NOT YET REGISTER | Kantor Pos Kpclk Sokaraja 53181 | Jl Jend Sudirman no. 101 | https://maps.app.goo.gl/rB2bApDGeYiiMx4F7 | Central Java | Sokaraja | Samiadji Huda | VGID-WO/BD/2026/II/0546 | 2026-03-06 | 2026-03-31 |  |  | New Power | 7.7kVA |  |  | 1 | [15 empty] | menunggu BA survey dari pihak Kantor Pos ke V-Green, info per 8 Apr
32 | SIGMATEC | BSS | SS Done | NOT YET REGISTER | Kantor Pos Kpclk Annex Notog | Jl Raya Notog | https://maps.app.goo.gl/DyUyCvfqGqnXRMt59 | Central Java | Notog | Samiadji Huda | VGID-WO/BD/2026/II/0546 | 2026-03-06 | 2026-03-31 |  |  | New Power | 7.7kVA |  |  | 1 | [15 empty] | menunggu BA survey dari pihak Kantor Pos ke V-Green, info per 8 Apr
33 | SIGMATEC | BSS | SS Done | NOT YET REGISTER | Kantor Pos KpcLK Wangon 53176 | Jl Raya Timur No. 10 | https://maps.app.goo.gl/Nr5g1RYhNaEcWTe1A | Central Java | Wangon | Samiadji Huda | VGID-WO/BD/2026/II/0546 | 2026-03-06 | 2026-03-31 |  |  | New Power | 7.7kVA |  |  | 1 | [15 empty] | menunggu BA survey dari pihak Kantor Pos ke V-Green, info per 8 Apr
34 | SIGMATEC | BSS | SS Done | NOT YET REGISTER | Kantor Pos Kpclk Annex Kemranjen | Jl. Ahmad Yani | https://maps.app.goo.gl/Y1bcJuYTyu4UBorG7 | Central Java | Kemranjen | Samiadji Huda | VGID-WO/BD/2026/II/0546 | 2026-03-06 | 2026-03-31 |  |  | New Power | 7.7kVA |  |  | 1 | [15 empty] | menunggu BA survey dari pihak Kantor Pos ke V-Green, info per 8 Apr
35 | SIGMATEC | BSS | SS Done | NOT YET REGISTER | Kantor Pos Kprk Purworejo | Jl Ahmad Yani no. 02 | https://maps.app.goo.gl/QVqkDuAX4FU2swwC6 | Central Java | Purworejo | Samiadji Huda | VGID-WO/BD/2026/II/0546 | 2026-03-09 | 2026-03-31 |  |  | New Power | 7.7kVA |  |  | 1 | [15 empty] | menunggu BA survey dari pihak Kantor Pos ke V-Green, info per 8 Apr
36 | SIGMATEC | BSS | SS Done | NOT YET REGISTER | Kantor Pos KpcLK Kutoarjo 54212 | Jl Kantor Pos no. 5 | https://maps.app.goo.gl/jEaGBAFtBmiCMoob8 | Central Java | Kutoarjo | Samiadji Huda | VGID-WO/BD/2026/II/0546 | 2026-03-31 | 2026-04-01 |  |  | New Power | 7.7kVA |  |  | 1 | [15 empty] | menunggu BA survey dari pihak Kantor Pos ke V-Green, info per 8 Apr
37 | SIGMATEC | BSS | SS Done | NOT YET REGISTER | Kantor Pos KpcLK Kaligesing 54175 | Ds Kaliharjo Kaligesing | https://maps.app.goo.gl/7G3hnaqnwQQps81A7 | Central Java | kaligesing | Samiadji Huda | VGID-WO/BD/2026/II/0546 | 2026-03-31 | 2026-04-01 |  |  | New Power | 7.7kVA |  |  | 1 | [15 empty] | menunggu BA survey dari pihak Kantor Pos ke V-Green, info per 8 Apr
38 | SIGMATEC | BSS | SS Done | NOT YET REGISTER | Kantor Pos KpcLK Kemiri 54262 | Jl Kerep RT 2 RW 1 | https://maps.app.goo.gl/Hg2ZZhfow7WiYKr76 | Central Java | Kemiri | Samiadji Huda | VGID-WO/BD/2026/II/0546 | 2026-03-31 | 2026-04-01 |  |  | New Power | 7.7kVA |  |  | 1 | [15 empty] | menunggu BA survey dari pihak Kantor Pos ke V-Green, info per 8 Apr
39 | SIGMATEC | BSS | SS Done | NOT YET REGISTER | Kantor Pos KpcLK Butuh > Relokasi Pituruh | Jl Brengkol Pituruh | https://maps.app.goo.gl/jo3hd7Bpc2UWdvY8A | Central Java | Pituruh | Samiadji Huda | VGID-WO/BD/2026/II/0546 | 2026-03-31 | 2026-04-01 |  |  | New Power | 7.7kVA |  |  | 1 | [15 empty] | menunggu BA survey dari pihak Kantor Pos ke V-Green, info per 8 Apr
40 | SIGMATEC | BSS | SS Done | NOT YET REGISTER | Kantor Pos KpcLK Kartosuro 57168 | Jl. Raya Solo-Yogya Pucangan | https://maps.app.goo.gl/99VYRQiakGUPPqb56 | Central Java | Kartosuro | Samiadji Huda | VGID-WO/BD/2026/II/0546 | 2026-03-31 | 2026-04-01 |  |  | New Power | 7.7kVA |  |  | 1 | [15 empty] | menunggu BA survey dari pihak Kantor Pos ke V-Green, info per 8 Apr
41 | SIGMATEC | BSS | SS Done | NOT YET REGISTER | Kantor Pos KpcDK Tipes 57127A < Relokasi dari Mojosongo | Jl Tangkuban Perahu Perumnas | https://maps.app.goo.gl/jo3hd7Bpc2UWdvY8A | Central Java | Mojosongo | Samiadji Huda | VGID-WO/BD/2026/II/0546 | 2026-03-31 | 2026-04-01 |  |  | New Power | 7.7kVA |  |  | 1 | [15 empty] | menunggu BA survey dari pihak Kantor Pos ke V-Green, info per 8 Apr
42 | SIGMATEC | BSS | SS Done | NOT YET REGISTER | Kantor Pos KpcLK Pracimantoro 57664 | Jl Raya Pracimantoro | https://maps.app.goo.gl/sMx8eUSV9ZGYCoJw6 | Central Java | Pracimantoro | Samiadji Huda | VGID-WO/BD/2026/II/0546 | 2026-03-31 | 2026-04-01 |  |  | New Power | 7.7kVA |  |  | 1 | [15 empty] | menunggu BA survey dari pihak Kantor Pos ke V-Green, info per 8 Apr
43 | SIGMATEC | BSS | SS Done | NOT YET REGISTER | Kantor Pos KpcLK Wuryantoro 57661 | Jl Raya Wuryantoro | https://maps.app.goo.gl/jz2VwjYHiQHLrYRM7 | Central Java | Wuryantoro | Samiadji Huda | VGID-WO/BD/2026/II/0546 | 2026-03-06 | 2026-03-31 |  |  | New Power | 7.7kVA |  |  | 1 | [15 empty] | menunggu BA survey dari pihak Kantor Pos ke V-Green, info per 8 Apr
44 | SIGMATEC | BSS | Site Survey | NOT YET REGISTER | Kantor Pos KpcLK Panggang 55872 | Ds. Panggang | https://maps.app.goo.gl/kHqNAzrb4kYeEdX99 | Central Java | Panggang | Samiadji Huda | VGID-WO/BD/2026/II/0546 |  |  |  |  | New Power | 7.7kVA |  |  | 1 | [15 empty] | menunggu konfirmasi dari regional
45 | SIGMATEC | BSS | Done Cons | NOT YET REGISTER | Planet Ban JALAN AFFANDI KLITREN | Jl. Gejayan No. 9, RT. 12, RW. 007, Kel. Klitren, Kec. Gondokusuman, Kota Yogyakarta | https://goo.gl/maps/G1v yQ95CnQEMuAw48 | Yogyakarta | Yogyakarta |  | (no WO survey) |  |  |  |  | New Power | 11kVA |  |  | 1 |  | VGID-WO/BD/2026/IV/0533 | 2026-04-14 | 2026-04-14 | [6 empty] | BSS-26011541000374
46 | SIGMATEC | BSS | Done Cons | NOT YET REGISTER | Planet Ban RAYA PALUR MOJOLABAN | Jl. Raya Palur No. 240, RT. 001, RW. 001, Kel. Palur, Kec. Mojolaban, Kab. Sukoharjo | https://goo.gl/maps/Qjy X5cktPpEWKgia9 | Central Java | Sukoharjo |  | (no WO survey) | [8 empty] | 1 |  | VGID-WO/BD/2026/IV/0533 | 2026-04-18 | 2026-04-18 | [6 empty] | BSS-255041000688
47 | SIGMATEC | BSS | Done Cons | WAITING PAYMENT | Planet Ban YOS SUDARSO SERENGAN | Jl. Yos Sudarso No. 294, RT. 001, RW. 001, Kel. Serengan, Kec. Serengan, Kotamadya Surakarta | https://goo.gl/maps/GLc kt4igBgG5VRJMA | Central Java | Surakarta |  | (no WO survey) |  |  |  |  | New Power | 7.7kVA |  |  | 1 |  | VGID-WO/BD/2026/IV/0533 | 2026-04-17 | 2026-04-17 | 2026-04-27 | wait VGRN |  |  |  |  | BSS-255141000891
48 | SIGMATEC | BSS | Done Cons | WAITING KWH | Planet Ban KOLONEL SUGIONO BRONTOKUSUMAN | Jl. Kolonel Sugiono No. 30 C, RT. 013, RW. 004, Kel. Brontokusuman, Kec. Mergangsan, Yogyakarta | https://goo.gl/maps/p49 3kikT4cauq8rN8 | Yogyakarta | Yogyakarta |  | (no WO survey) |  |  |  |  | New Power | 11kVA |  |  | 1 |  | VGID-WO/BD/2026/IV/0533 | 2026-04-13 | 2026-04-13 | 2026-04-18 | 2026-04-23 |  |  |  |  | BSS-26011541000051
49 | SIGMATEC | BSS | Done Cons | WAITING PAYMENT | Planet Ban BANTUL DONGKELAN PANGGUNGHARJO | Jl. Bantul Dongkelan No. 176, RT. 005, RW. 016, Kel. Panggungharjo, Kec. Sewon, Kab. Bantul | https://goo.gl/maps/2dZ MJnRsTJXjWyTK6 | Yogyakarta | Bantul |  | (no WO survey) |  |  |  |  | New Power | 7.7kVA |  |  | 1 |  | VGID-WO/BD/2026/IV/0533 | 2026-04-12 | 2026-04-12 | 2026-04-15 | wait VGRN |  |  |  |  | BSS-255141000803
50 | SIGMATEC | BSS | Done Cons | WAITING KWH | Planet Ban JALAN WATES NGESTIHARJO | Jl. Wates No. 25, RT. 009. RW. 027, Kel. Ngestiharjo, Kec. Kasihan, Kab. Bantul | https://goo.gl/maps/tVg s7XciBLRr7h4e6 | Yogyakarta | Bantul |  | (no WO survey) |  |  |  |  | New Power | 7.7kVA |  |  | 1 |  | VGID-WO/BD/2026/IV/0533 | 2026-04-11 | 2026-04-11 | 2026-04-15 | 2026-04-23 |  |  |  |  | BSS-255041000948
51 | SIGMATEC | BSS | Done Cons | WAITING KWH | Planet Ban KYAI MOJO BENER | Jl. Kyai Mojo 86B 86C, RT. 12, RW. 07, Kel. Bener, Kec. Tegal Rejo, Kota Jogjakarta Jawa Tengah | https://goo.gl/maps/iKJ MYzz9k3n6PLvh9 | Yogyakarta | Yogyakarta |  | (no WO survey) |  |  |  |  | New Power | 11kVA |  |  | 1 |  | VGID-WO/BD/2026/IV/0533 | 2026-04-13 | 2026-04-13 | 2026-04-22 | 2026-04-28 |  |  |  |  | BSS-26011541000395
52 | SIGMATEC | BSS | Done Cons | NOT YET REGISTER | Planet Ban DR RAJIMAN PANULARAN | Jl Dr Rajiman No 415 Rt 02 Rw 01 Kel Panularan Kec Laweyan Kota Surakarta | https://goo.gl/maps/tiPiBiZpUjPo62FM7 | Central Java | SURAKARTA |  | (no WO survey) | [8 empty] | 1 |  | VGID-WO/BD/2026/IV/0533 | 2026-04-17 | 2026-04-17 | [6 empty] | BSS-255141000885
53 | SIGMATEC | BSS | Done Cons | WAITING KWH | Planet Ban JALAN TIDAR SIDANEGARA | Jl Tidar No 99 Kel. Sidanegara Kec. Cilacap Tengah Kabupaten Cilacap | https://goo.gl/maps/5G VAnpWKZent81rz5 | Central Java | CILACAP |  | (no WO survey) |  |  |  |  | New Power | 7.7kVA |  |  | 1 |  | VGID-WO/BD/2026/IV/0533 | 2026-04-19 | 2026-04-19 | 2026-04-20 | 2026-04-23 |  |  |  | 2026-04-24 | BSS-255141000816
54 | SIGMATEC | BSS | Done Cons | WAITING PAYMENT | Planet Ban JALAN PENGASINAN TANJUNG | Jl Pahlawan Rt 001 Rw 002 Kel Tanjung Kec Purwokerto Selatan Kab Banyumas (Jl. Pengasinan) | https://goo.gl/maps/SCe PpgaYJKskwmLP9 | Central Java | Banyumas |  | (no WO survey) |  |  |  |  | New Power | 7.7kVA |  |  | 1 |  | VGID-WO/BD/2026/IV/0533 | 2026-04-16 | 2026-04-16 | 2026-04-27 | wait VGRN |  |  |  |  | BSS-255041000675
55 | SIGMATEC | BSS | Done Cons | WAITING PAYMENT | Planet Ban JALAN DIPONEGORO SINDANGSARI | Jl Diponegoro Blok 013 Rt 004 Rw 005 Kel Sindangsari Kec Majenang Kabupaten Cilacap | https://goo.gl/maps/k8q fdERDCowzuunT6 | Central Java | CILACAP |  | (no WO survey) | [8 empty] | 1 |  | VGID-WO/BD/2026/IV/0533 | 2026-04-18 | 2026-04-18 | 2026-04-20 | wait VGRN |  |  |  |  | BSS-255141000862
56 | SIGMATEC | BSS | Done Cons | WAITING PAYMENT | Planet Ban ADI SUMARMO NGABEAN | Jl Adisumarmo No 15, RT. 003, RW. 002, Kel. Ngabean Kartasura, Kec. Kartasura, Kabupaten Sukoharjo | https://goo.gl/maps/dP UHvoLHBLirHFKf6 | Central Java | Sukoharjo |  | (no WO survey) |  |  |  |  | New Power | 7.7kVA |  |  | 1 |  | VGID-WO/BD/2026/IV/0533 | 2026-04-16 | 2026-04-16 | 2026-04-27 | wait VGRN |  |  |  |  | BSS-255041000704
57 | SIGMATEC | BSS | Drop | NOT YET REGISTER | Planet Ban BRIGJEN KATAMSO WATES | Jl. Brigjen Katamso No. 74, Kel. Wates, Kec. Wates, Kab. Kulon Progo | https://maps.app.goo.gl/ 2HgeLz3KMGBWniQr7 | Central Java | Kulon Progo |  | (no WO survey) | [8 empty] | 1 |  | VGID-WO/BD/2026/IV/0533 | - | - | - | - |  |  |  |  | - |  |  |  |  | toko akan pindah di bln Juni 2026 | -
58 | SIGMATEC | BSS | Done Cons | NOT YET REGISTER | Planet Ban PROF SUPOMO BANTUL | Jl Prof Supomo No 01 Rt 01 Rw 05 Kel Bantul Kec Bantul Kab Bantul Jawa Tengah | https://goo.gl/maps/BN Wr9nujgsCzsxR96 | Yogyakarta | Bantul |  | (no WO survey) |  |  |  |  | New Power | 7.7kVA |  |  | 1 |  | VGID-WO/BD/2026/IV/0533 | 2026-04-11 | 2026-04-11 | [6 empty] | BSS-255141000668
59 | SIGMATEC | BSS | Done Cons | WAITING KWH | Planet Ban JALAN PEMUDA TRIDADI | Jl Pemuda No 09 Km 12 Rt 003 Rw 001Kel Wadas Sridadi Kec Sleman Kab Sleman Jateng | https://goo.gl/maps/U7e GNWdyuHfmyhCU8 | Yogyakarta | SLEMAN |  | (no WO survey) |  |  |  |  | New Power | 7.7kVA |  |  | 1 |  | VGID-WO/BD/2026/IV/0533 | 2026-04-11 | 2026-04-11 | 2026-04-16 | 2026-04-23 |  |  |  |  | BSS-255141000690
60 | SIGMATEC | BSS | Done Cons | NOT YET REGISTER | Planet Ban RAYA JOGONALAN PELAWIKAN | Jl Raya Jogonalan No 113 Rt 002 Rw 003 Kel Pelawikan Kec Jogonalan Kab Klaten Jateng | https://goo.gl/maps/wkt fdvDH7HvXZCZz5 | Central Java | Klaten |  | (no WO survey) | [8 empty] | 1 |  | VGID-WO/BD/2026/IV/0533 | 2026-04-14 | 2026-04-14 | [6 empty] | BSS-255141000839
61 | SIGMATEC | BSS | Done Cons | WAITING PAYMENT | Planet Ban YOS SUDARSO SELOKERTO | Jl Yos Sudarso No 458 Rt 002 Rw 001 Kel Selokerto Kec Sempor Kab Kebumen Jateng | https://maps.app.goo.gl/ prp29a3y1AX2Jf3HA | Central Java | KEBUMEN |  | (no WO survey) |  |  |  |  | New Power | 7.7kVA |  |  | 1 |  | VGID-WO/BD/2026/IV/0533 | 2026-04-16 | 2026-04-16 | 2026-04-21 | wait VGRN |  |  |  |  | BSS-255141000422
62 | SIGMATEC | BSS | Done Cons | WAITING KWH | Planet Ban JALAN MAGELANG BLONDO | Jl Raya Jogja Magelang Kel Blondo Kec Mungkid Kab Magelang | https://goo.gl/maps/fZs h17T7EeRvNjiR6 | Central Java | Magelang |  | (no WO survey) |  |  |  |  | New Power | 7.7kVA |  |  | 1 |  | VGID-WO/BD/2026/IV/0533 | 2026-04-15 | 2026-04-15 | 2026-04-23 | 2026-04-28 |  |  |  |  | BSS-254941002179
63 | SIGMATEC | BSS | Done Cons | WAITING PAYMENT | Planet Ban TENTARA PELAJAR SOKANANDI | Jl. Tentara Pelajar Km. 5, Rt.003/004, Kel.Sokanandi, Kec. Banjarnegara, Banjarnegara Kab | https://maps.app.goo.gl/ 5KSFDB14PXHmkDK2A | Central Java | Banjarnegara |  | (no WO survey) |  |  |  |  | New Power | 7.7kVA |  |  | 1 |  | VGID-WO/BD/2026/IV/0533 | 2026-04-18 | 2026-04-18 | 2026-04-27 | wait VGRN |  |  |  |  | BSS-255141000646
64 | SIGMATEC | BSS | Done Cons | WAITING PAYMENT | Planet Ban PERINTIS KEMERDEKAAN KEBONMANIS | Jl. Perintis Kemerdekaan No. 93-95 Rt001/03 Kel.Kebon Manis Kec. Cilacap Utara, Kabupaten Cilacap, | https://goo.gl/maps/7b5 mtm2hERpiKTBu6 | Central Java | CILACAP |  | (no WO survey) | [8 empty] | 1 |  | VGID-WO/BD/2026/IV/0533 | 2026-04-17 | 2026-04-17 | 2026-04-20 | wait VGRN |  |  |  |  | BSS-254741001272
65 | SIGMATEC | BSS | Done Cons | NOT YET REGISTER | Planet Ban SLAMET RIYADI JOHO | Jl.Slamet Riyadi No 01 Rt 002 Rw 003 Kel Joho Kec Sukoharjo Kab Sukoharjo | https://goo.gl/maps/giA h25NeAe5gQ8EK8 | Central Java | Sukoharjo |  | (no WO survey) | [8 empty] | 1 |  | VGID-WO/BD/2026/IV/0533 | 2026-04-18 | 2026-04-18 | [6 empty] | BSS-255141000775
66 | SIGMATEC | BSS | Done Cons | NOT YET REGISTER | Planet Ban TUMENGGUNG JOGONEGORO TAWANGSARI | Jl.Tumenggung Jogonegoro Rt 007 Rw 002 Kel Tawang Sari Kec Wonosobo Kab Wonosobo | https://maps.app.goo.gl/ xAic3zHhoWFTZTxm7 | Central Java | WONOSOBO |  | (no WO survey) | [8 empty] | 1 |  | VGID-WO/BD/2026/IV/0533 | 2026-04-17 | 2026-04-17 | [6 empty] | BSS-255141000608
67 | SIGMATEC | BSS | Done Cons | NOT YET REGISTER | Planet Ban BRIGJEN KATAMSO PANGENREJO << HM SARBINI KUTOSARI | ... << Jl HM Sarbini No.13 RT.05 RW.04 Kel. Kutosari Kec. Kebumen Kabupaten Kebumen | https://maps.app.goo.gl/ srkVf7urpiPnq3Lf6 | Central Java | Purworejo |  | (no WO survey) | [8 empty] | 1 |  | VGID-WO/BD/2026/IV/0533 | 2026-04-29 | 2026-04-29 | [11 empty] | pengganti << DROP by V-Green
68 | SIGMATEC | BSS | Done Cons | WAITING KWH | Planet Ban PURWOREJO MAGELANG PAKELAN | Jl Purworejo Magelang Km1 Rt 002 Rw 003 Kel Pakelan Kec Mertoyudan Kab Magelang Jawa Tengah | https://maps.app.goo.gl/ hwia1e157vovmVnY6 | Central Java | Magelang |  | (no WO survey) |  |  |  |  | New Power | 7.7kVA |  |  | 1 |  | VGID-WO/BD/2026/IV/0533 | 2026-04-15 | 2026-04-15 | 2026-04-23 | 2026-04-28 |  |  |  |  | BSS-255141000658
69 | SIGMATEC | BSS | Done Cons | NOT YET REGISTER | Planet Ban JALAN TEGALGENDU PRENGGAN | Jl. Tegalgendu No. 17, RT. 052, RW.011, Kel. Prenggan, Kec. Kota Gede, Yogyakarta, DIY | https://goo.gl/maps/EXT 59auhgeudZXCp8 | Yogyakarta | Yogyakarta |  | (no WO survey) |  |  |  |  | New Power | 11kVA |  |  | 1 |  | VGID-WO/BD/2026/IV/0533 | 2026-04-14 | 2026-04-14 | [6 empty] | BSS-26011641000230
70 | SIGMATEC | BSS | Done Cons | WAITING PAYMENT | Planet Ban SOLO YOGYA TIRTOMARTANI | Jl Solo Yogya Km 14 Rt 000 Rw 000 Kel Tirtomartani Kec Kalasan Kab Sleman Jawa Tengah | https://goo.gl/maps/FJjo Yz1MT9m27cXW9 | Yogyakarta | SLEMAN |  | (no WO survey) |  |  |  |  | New Power | 7.7kVA |  |  | 1 |  | VGID-WO/BD/2026/IV/0533 | 2026-04-13 | 2026-04-13 | 2026-04-18 | wait VGRN |  |  |  |  | BSS-255041000826
71 | SIGMATEC | BSS | Done Cons | NOT YET REGISTER | Planet Ban RAYA SUKOWATI JETAK | Jl. Raya Sukowati No.120 Rt 04 Rw 08 Kel Jetak Kec Sidoharjo Kab Sragen | https://goo.gl/maps/wK YhbF6fNtwDGVoK9 | Central Java | SRAGEN |  | (no WO survey) | [8 empty] | 1 |  | VGID-WO/BD/2026/IV/0533 | 2026-04-19 | 2026-04-19 | [6 empty] | BSS-255141000627
72 | SIGMATEC | BSS | Done Cons | WAITING PAYMENT | Planet Ban AHMAD DAHLAN PURWOREJO | Jl. KH Ahmad Dahlan No. 55 B RT. 002/009, Kel. Purworejo Kec. Purworejo kab. Purworejo | https://maps.app.goo.gl/ MXArutRpZ9RNMtY16 | Central Java | PURWOREJO |  | (no WO survey) |  |  |  |  | New Power | 7.7kVA |  |  | 1 |  | VGID-WO/BD/2026/IV/0533 | 2026-04-13 | 2026-04-14 | 2026-04-28 | wait VGRN |  |  |  |  | BSS-255141000643
73 | SIGMATEC | BSS | Done Cons | WAITING KWH | Planet Ban SETURAN CONDONG CATUR | Jl. Seturan Raya No. 414 Rt 07 Rw 016 Kel Condong Catur Kec. Depok Kab. Sleman | https://goo.gl/maps/dV2 J2aT4hSthrAN86 | Yogyakarta | SLEMAN |  | (no WO survey) |  |  |  |  | New Power | 7.7kVA |  |  | 1 |  | VGID-WO/BD/2026/IV/0533 | 2026-04-13 | 2026-04-13 | 2026-04-18 | 2026-04-23 |  |  |  |  | BSS-255041000682
74 | SIGMATEC | BSS | Done Cons | WAITING KWH | Planet Ban JALAN RAYA MERTOYUDAN | Jl. Raya Mertoyudan No. 441, Rt. 002, Rw. 001, Kel. Mertoyudan, Kec. Mertoyudan, Kab. Magelang | https://maps.app.goo.gl/ AkGVZbELKuAwJZMNA | Central Java | Magelang |  | (no WO survey) |  |  |  |  | New Power | 7.7kVA |  |  | 1 |  | VGID-WO/BD/2026/IV/0533 | 2026-04-15 | 2026-04-15 | 2026-04-23 | 2026-04-28 |  |  |  |  | BSS-255041000900
75 | SIGMATEC | BSS | Done Cons | WAITING PAYMENT | Planet Ban YOS SUDARSO KARANGLEWASLOR | Jl. Yos Sudarso No. 133 Rt 01 Rw 04 Kelurahan Karanglewas Lor Kecamatan Purwokerto Barat Kabupaten Banyumas | https://goo.gl/maps/Cpv PmTJB6TceaZvy8 | Central Java | BANYUMAS |  | (no WO survey) |  |  |  |  | New Power | 7.7kVA |  |  | 1 |  | VGID-WO/BD/2026/IV/0533 | 2026-04-15 | 2026-04-15 | 2026-04-27 | wait VGRN |  |  |  |  | BSS-255141000500
76 | SIGMATEC | BSS | Done Cons | NOT YET REGISTER | Planet Ban JENDRAL SUDIRMAN SIDAREJA 2 << RAYA AJIBARANG WETAN | ... << Jl. Ajibarang Raya, Rt. 02/003, Kel. Ajibarang Wetan Kec. Ajibarang. Kab. Banyumas | https://goo.gl/maps/Dq RUpqndvsoC8Zo37 | Central Java | Cilacap |  | (no WO survey) | [8 empty] | 1 |  | VGID-WO/BD/2026/IV/0533 | 2026-04-29 | 2026-04-29 | [11 empty] | pengganti << DROP by V-Green
77 | SIGMATEC | BSS | Done Cons | WAITING PAYMENT | Planet Ban AW SUMARMO PURBALINGGALOR | Jl. Aw Sumarmo, Rt. 002, Rw. 002, Kel. Purbalingga Lor, Kec. Purbalingga, Kab. Purbalingga | https://goo.gl/maps/VUx LjdwdCmuA8k5VA | Central Java | Purbalingga |  | (no WO survey) |  |  |  |  | New Power | 7.7kVA |  |  | 1 |  | VGID-WO/BD/2026/IV/0533 | 2026-04-17 | 2026-04-17 | 2026-04-27 | wait VGRN |  |  |  |  | BSS-255141000893
78 | SIGMATEC | BSS | Done Cons | DONE KWH | Planet Ban KAPTEN HARYADI SARIHARJO | Jl. Kapten Haryadi, RT.001, RW. 002, Kel. Sariharjo, Kec. Ngaglik, kab. Sleman | https://goo.gl/maps/w6L u5eyG1314pK6J8 | Yogyakarta | SLEMAN |  | (no WO survey) |  |  |  |  | New Power | 7.7kVA |  |  | 1 |  | VGID-WO/BD/2026/IV/0533 | 2026-04-13 | 2026-04-13 | 2026-04-18 | 2026-04-23 |  |  |  | 2026-04-29 | BSS-255141000637
79 | SIGMATEC | BSS | Done Cons | NOT YET REGISTER | Planet Ban AM SANGAJI KARANGWARU | Jl AM Sangaji No. 102 Kelurahan Karangwaru Kecamatan Tegalrejo Kota Yogyakarta | https://goo.gl/maps/zk1 6Nsx5698QogwXA | Yogyakarta | Yogyakarta |  | (no WO survey) |  |  |  |  | New Power | 11kVA |  |  | 1 |  | VGID-WO/BD/2026/IV/0533 | 2026-04-14 | 2026-04-14 | [6 empty] | BSS-260241000275
80 | SIGMATEC | BSS | Done Cons | NOT YET REGISTER | Planet Ban JALAN HASANUDIN MANGUNSARI | Jl Hasanudin No. 6A Kelurahan Mangunsari Kecamatan Sidomukti Kota Salatiga | https://goo.gl/maps/5B G3ZX8o7g3kunEN7 | Central Java | SALATIGA |  | (no WO survey) | [8 empty] | 1 |  | VGID-WO/BD/2026/IV/0533 | 2026-04-18 | 2026-04-18 | [6 empty] | BSS-26011541000281
81 | SIGMATEC | BSS | Done Cons | WAITING PAYMENT | Planet Ban DR RAJIMAN PAJANG | Jl Dr Rajiman No 662 Kelurahan Pajang Kecamatan Laweyan Kota Surakarta | https://goo.gl/maps/4Jh oM5GAvKD8Vy2Y8 | Central Java | SURAKARTA |  | (no WO survey) |  |  |  |  | New Power | 7.7kVA |  |  | 1 |  | VGID-WO/BD/2026/IV/0533 | 2026-04-16 | 2026-04-16 | 2026-04-27 | wait VGRN |  |  |  |  | BSS-255141000726
82 | SIGMATEC | BSS | Done Cons | NOT YET REGISTER | Planet Ban LETJEN SUPRAPTO SUMBER | Jl. Letjen Suprapto No. 79 Kel. Sumber Kec. Banjarsari Kota Surakarta | https://goo.gl/maps/txS CRqqziwE2ayLz8 | Central Java | SURAKARTA |  | (no WO survey) | [8 empty] | 1 |  | VGID-WO/BD/2026/IV/0533 | 2026-04-19 | 2026-04-19 | [6 empty] | BSS-255041000828
83 | SIGMATEC | BSS | Done Cons | WAITING PAYMENT | Planet Ban AHMAD YANI KANDANGGAMPANG | Jl. Ahmad Yani No. 65C, Kel. Gampang, Kec. Purbalingga, Kab. Purbalingga | https://goo.gl/maps/fza 39otjRzwf6MdM9 | Central Java | Purbalingga |  | (no WO survey) |  |  |  |  | New Power | 7.7kVA |  |  | 1 |  | VGID-WO/BD/2026/IV/0533 | 2026-04-17 | 2026-04-17 | 2026-04-27 | wait VGRN |  |  |  |  | BSS-255141000874
84 | SIGMATEC | BSS | Done Cons | NOT YET REGISTER | Planet Ban DR SOEPARNO KARANGWANGKAL 2 << JENDRAL SUDIRMAN SOKARAJATENGAH | ... << Jl. Jendral Sudirman No. 157B RT. 03/05, Desa. Sokaraja Tengah, Kec. Sokaraja, Kab. Banyumas | https://goo.gl/maps/rxS V5zzGwxoJu3iz6 | Central Java | Banyumas |  | (no WO survey) | [8 empty] | 1 |  | VGID-WO/BD/2026/IV/0533 | 2026-04-29 | 2026-04-29 | [11 empty] | pengganti << DROP by V-Green
85 | SIGMATEC | BSS | Done Cons | WAITING PAYMENT | Planet Ban GUNUNG TUGEL KARANGKLESEM | Jl Gunung Tugel No 970 RT 03/09 Kel Karang Klesem Kec Purwekerto Selatan Kab Banyumas | https://goo.gl/maps/q49 tDayBMvDiVbG3A | Central Java | BANYUMAS |  | (no WO survey) |  |  |  |  | New Power | 7.7kVA |  |  | 1 |  | VGID-WO/BD/2026/IV/0533 | 2026-04-16 | 2026-04-16 | 2026-04-27 | wait VGRN |  |  |  |  | BSS-255141000819
86 | SIGMATEC | BSS | Done Cons | WAITING PAYMENT | Planet Ban MARTIDIREJA PURWOKERTO WETAN | Jl Martidireja 1 No 56 Kel Purwokerto Wetan Kec Purwokerto Timur Kab Banyumas | https://goo.gl/maps/8ZQ pA2jnruimsu4p9 | Central Java | BANYUMAS |  | (no WO survey) |  |  |  |  | New Power | 7.7kVA |  |  | 1 |  | VGID-WO/BD/2026/IV/0533 | 2026-04-18 | 2026-04-18 | 2026-04-27 | wait VGRN |  |  |  |  | BSS-255041000679
87 | SIGMATEC | BSS | Done Cons | WAITING PAYMENT | Planet Ban LETJENPOL SOEMARTO PURWANEGARA | Jl. Letjen Pol Soemarto RT.05/RW.02, Kel. Purwanegara, Kec. Purwokerto Utara, Kab. Banyumas | https://goo.gl/maps/1hV GHVsZEA4PBs299 | Central Java | Banyumas |  | (no WO survey) |  |  |  |  | New Power | 7.7kVA |  |  | 1 |  | VGID-WO/BD/2026/IV/0533 | 2026-04-17 | 2026-04-17 | 2026-04-27 | wait VGRN |  |  |  |  | BSS-255141000779
88 | SIGMATEC | BSS | On Cons | NOT YET REGISTER | Planet Ban SOEKARNO HATTA CEPIRING << RAYA PEMUDA KEBUMEN | Jl. Soekarno Hatta No 114, Rt. 008, Rw. 001, Kel. Cepiring Botomulyo | https://maps.app.goo.gl/ CAxqqhXCgLpr2qZPA | Central Java | Kendal |  | (no WO survey) | [8 empty] | 1 |  | VGID-WO/BD/2026/IV/0533 | [13 empty] | pengganti << DROP by V-Green
89 | SIGMATEC | BSS | Done Cons | WAITING PAYMENT | Planet Ban JALAN PEMUDA MUNTILAN | Jl. Pemuda No.198A, RT.003, RW.023, Kel. Gunungpring, Kec. Muntilan, Kab. Magelang | https://goo.gl/maps/vsQ KoA4fZPdESWns7 | Central Java | Magelang |  | (no WO survey) |  |  |  |  | New Power | 7.7kVA |  |  | 1 |  | VGID-WO/BD/2026/IV/0533 | 2026-04-14 | 2026-04-14 | 2026-04-23 | wait VGRN |  |  |  |  | BSS-255141000939
90 | SIGMATEC | BSS | Done Cons | NOT YET REGISTER | Planet Ban GEDONG KUNING REJOWINANGUN | Jl. Gedong Kuning No. 8 Kel. Rejowinangun Kec. Kota Gede Kota Yogyakarta | https://goo.gl/maps/wf2 iEoTZ2wXY3tp99 | Yogyakarta | Yogyakarta |  | (no WO survey) |  |  |  |  | New Power | 11kVA |  |  | 1 |  | VGID-WO/BD/2026/IV/0533 | 2026-04-14 | 2026-04-14 | [6 empty] | BSS-26011541000360
91 | SIGMATEC | BSS | Done Cons | NOT YET REGISTER | Planet Ban SLAMET RIYADI KARTASURA << PANGERAN DIPONEGORO KUTOARJO | ... << Jl. Pangeran Diponegoro No. 109 Kel. Kutoarjo, Kec. Kutoarjo, Kab. Purworejo | https://maps.google.co m/?cid=2551955476692 900432&entry=gps | Central Java | Sukoharjo |  | (no WO survey) | [8 empty] | 1 |  | VGID-WO/BD/2026/IV/0533 | 2026-04-29 | 2026-04-29 | [11 empty] | pengganti << DROP by V-Green
92 | SIGMATEC | BSS | Done Cons | WAITING KWH | Planet Ban AHMAD YANI KROYA | Jl. Ahmad Yani No. 8 RT.20/03 Kelurahan Kroya Ke. Kroya Kab. Cilacap | https://goo.gl/maps/Aju HQeBjyEMdUp2p8 | Central Java | CILACAP |  | (no WO survey) |  |  |  |  | New Power | 7.7kVA |  |  | 1 |  | VGID-WO/BD/2026/IV/0533 | 2026-04-18 | 2026-04-18 | 2026-04-20 | 2026-04-23 |  |  |  | jumat | BSS-260141002085
93 | SIGMATEC | BSS | Done Cons | NOT YET REGISTER | Planet Ban SULTAN AGUNG PURWOKINANTI | Jl. Sultan Agung No. 3 Kel. Purwokinanti, Kec. Pakualaman Kota Yogyakarta | https://goo.gl/maps/pA Mxr834AAxRWi7j8 | Yogyakarta | Yogyakarta |  | (no WO survey) |  |  |  |  | New Power | 11kVA |  |  | 1 |  | VGID-WO/BD/2026/IV/0533 | 2026-04-14 | 2026-04-14 | [6 empty] | BSS-26011641000256
94 | SIGMATEC | BSS | Done Cons | WAITING PAYMENT | Planet Ban SOEKARNO HATTA MEWEK | Jl. Soekarno Hatta RT 01 RW 01, Kel. Mewek, Kec. Kalimanah, Kab. Purbalingga | https://maps.app.goo.gl/ Qz7mJypFHccnx6Mz8 | Central Java | Purbalingga |  | (no WO survey) |  |  |  |  | New Power | 7.7kVA |  |  | 1 |  | VGID-WO/BD/2026/IV/0533 | 2026-04-18 | 2026-04-18 | 2026-04-27 | wait VGRN |  |  |  |  | BSS-255141000632
95 | SIGMATEC | BSS | Done Cons | NOT YET REGISTER | Planet Ban JALAN PURWOMARTANI KALASAN << LAKSDA ADISUCIPTO CATURTUNGGAL | ... << Jl. Raya Solo Km. 7 No. 165 Rt.2/1 Kel. Catur Tunggal Kec. Depok Kab. Sleman | https://maps.app.goo.gl/ oM2ccScbPSYf3P258 | Yogyakarta | SLEMAN |  | (no WO survey) | [8 empty] | 1 |  | VGID-WO/BD/2026/IV/0533 | 2026-04-29 | 2026-04-29 | [11 empty] | pengganti << DROP by V-Green
96 | SIGMATEC | BSS | Done Cons | NOT YET REGISTER | Planet Ban JALAN PANDANARAN KIRINGAN | Jl. Pandanaran No. 316, Rt.02/02, Kel. Kiringan, Kec. Boyolali, Kab. Boyolali | https://goo.gl/maps/7Xh 3N3erWVKXEPpb9 | Central Java | BOYOLALI |  | (no WO survey) | [8 empty] | 1 |  | VGID-WO/BD/2026/IV/0533 | 2026-04-16 | 2026-04-16 | [6 empty] | BSS-255141000449
97 | SIGMATEC | BSS | Done Cons | WAITING PAYMENT | Planet Ban JALAN PEDAN KEDEN | Jl. Pedan Cawas, Km. 0,1, Desa. Keden, Kec. Pedan, Kab. Klaten | https://goo.gl/maps/BTa TNnadPUi5m41SA | Central Java | Klaten |  | (no WO survey) |  |  |  |  | New Power | 7.7kVA |  |  | 1 |  | VGID-WO/BD/2026/IV/0533 | 2026-04-15 | 2026-04-15 | 2026-04-23 | wait VGRN |  |  |  |  | BSS-255141000574
98 | SIGMATEC | BSS | Done Cons | NOT YET REGISTER | Planet Ban KAPTEN MULYADI PASARKLIWON | Jl. Kapten Mulyadi, RT. 002, RW. 11,Kel. Pasar Kliwon, Kec. Pasar Kliwon, Kota. Surakarta | https://goo.gl/maps/gNt NndJMsSjCBnZeA | Central Java | SURAKARTA |  | (no WO survey) | [8 empty] | 1 |  | VGID-WO/BD/2026/IV/0533 | 2026-04-20 | 2026-04-20 | [6 empty] | BSS-255141000659
99 | SIGMATEC | BSS | Done Cons | NOT YET REGISTER | Planet Ban JALAN RAJAWALI KABUPATEN | Jl. Rajawali No. 93, Rt. 003, Rw. 001, Kel. Kabupaten, Kec. Kota Klaten, Kab. Klaten | https://goo.gl/maps/Jrd Qia2pM1KMTYbX7 | Central Java | Klaten |  | (no WO survey) | [8 empty] | 1 |  | VGID-WO/BD/2026/IV/0533 | 2026-04-14 | 2026-04-14 | [6 empty] | BSS-255141000764
100 | SIGMATEC | BSS | Done Cons | WAITING KWH | Planet Ban AMIR PATINAMA SIDOAGUNG | Jl. Amir Patinama No. 2, Rt. 000/000, Kel. Sidoagung, Kec. Godean, Kab. Sleman | https://goo.gl/maps/Fx mGffp8fc3CKL7EA | Yogyakarta | SLEMAN |  | (no WO survey) | [8 empty] | 1 |  | VGID-WO/BD/2026/IV/0533 | 2026-04-13 | 2026-04-13 | 2026-04-18 | 2026-04-23 |  |  |  |  | BSS-255141000943
101 | SIGMATEC | BSS | Done Cons | WAITING PAYMENT | Planet Ban SENOPATI RAYA DUKUHWALUH | Jl Senopati Raya No. 23, Rt. 001, Rw. 010, Kel. Dukuhwaluh, Kec. Kembaran, Kab. Banyumas | https://goo.gl/maps/26K mX3hQdqRfWUHQ9 | Central Java | BANYUMAS |  | (no WO survey) |  |  |  |  | New Power | 7.7kVA |  |  | 1 |  | VGID-WO/BD/2026/IV/0533 | 2026-04-18 | 2026-04-18 | 2026-04-27 | wait VGRN |  |  |  |  | BSS-255141000831
102 | SIGMATEC | BSS | Done Cons | NOT YET REGISTER | Planet Ban JALAN SUMARWI WONOSARI | Jl. Sumarwi No. 1, Rt. 010, Rw. 001, Kel. Wonosari, Kec. Wonosari, Kab. Gunungkidul | https://maps.app.goo.gl/ aeRfKvstSuoiwtCT8 | Central Java | Gunung Kidul |  | (no WO survey) | [8 empty] | 1 |  | VGID-WO/BD/2026/IV/0533 | 2026-04-17 | 2026-04-17 | [6 empty] | BSS-255141000953
103 | SIGMATEC | BSS | Done Cons | WAITING PAYMENT | Planet Ban JALAN RAYA SALAMAN | Jl. Raya Salaman No. 123, Kel. Salaman, Kec. Salaman, Kab. Magelang | https://maps.app.goo.gl/ 6ZGveNk6U3njHYeJ8 | Central Java | Magelang |  | (no WO survey) |  |  |  |  | New Power | 7.7kVA |  |  | 1 |  | VGID-WO/BD/2026/IV/0533 | 2026-04-14 | 2026-04-14 | 2026-04-27 | wait VGRN |  |  |  |  | BSS-255141000808
104 | SIGMATEC | BSS | Done Cons | WAITING KWH | Planet Ban JALAN PARANGTRITIS MANTRIJERON | Jl. Parangtritis No. 148, Rt. 46, Rw. 12, Kel. Mantrijeron, Kec. Mantrijeron, Kota. Yogyakarta | https://goo.gl/maps/CQ qzQF5r7NPL2Xse7 | Yogyakarta | Yogyakarta |  | (no WO survey) |  |  |  |  | New Power | 11kVA |  |  | 1 |  | VGID-WO/BD/2026/IV/0533 | 2026-04-14 | 2026-04-14 | 2026-04-18 | 2026-04-23 |  |  |  |  | BSS-260241000093
105 | SIGMATEC | BSS | Done Cons | NOT YET REGISTER | Planet Ban PB AHMAD YANI WEDI | Jl. Ahmad Yani No. 5B RT.010/RW.005 | https://goo.gl/maps/C1t kSPtL6KotG96T6 | Central Java | Klaten |  | (no WO survey) | [8 empty] | 1 |  | VGID-WO/BD/2026/IV/0533 | 2026-04-14 | 2026-04-14 | [6 empty] | BSS-255141000505
106 | SIGMATEC | BSS | Done Cons | WAITING KWH | Planet Ban NGIPIK BATURETNO BANGUNTAPAN | Jl. Ngipik No. 48 RT.001/RW.016, Kel. Baturetno, Kec. Banguntapan, Kab. Bantul | https://goo.gl/maps/kKV kKBVae511jfsp8 | Yogyakarta | Bantul |  | (no WO survey) |  |  |  |  | New Power | 7.7kVA |  |  | 1 |  | VGID-WO/BD/2026/IV/0533 | 2026-04-12 | 2026-04-12 | 2026-04-15 | 2026-04-28 |  |  |  |  | BSS-255041000629
107 | SIGMATEC | BSS | Done Cons | WAITING PAYMENT | Planet Ban RAYA DELANGGU KLATEN | Jalan Raya Delanggu No.113 RT 003/003 Kel. Boto, Jogopotro, Sabrang, Kec. Delanggu, Kabupaten Klaten, Jawa Tengah 57471 | https://goo.gl/maps/KYh DPmyCW22cpx8JA | Central Java | Klaten |  | (no WO survey) | [8 empty] | 1 |  | VGID-WO/BD/2026/IV/0533 | 2026-04-15 | 2026-04-15 | 2026-04-23 | wait VGRN |  |  |  |  | BSS-255141000413
108 | SIGMATEC | BSS | Done Cons | WAITING PAYMENT | Planet Ban RAYA JATINOM BONYOKAN | Jl. Raya Jatinom - Klaten Km. 0,2, Rt. 005, Rw. 002, Desa. Bonyokan, Kec. Jatinom, Kab. Klaten | https://goo.gl/maps/cUi X1nhqSvsaJgHv6 | Central Java | Klaten |  | (no WO survey) | [8 empty] | 1 |  | VGID-WO/BD/2026/IV/0533 | 2026-04-15 | 2026-04-15 | 2026-04-23 | wait VGRN |  |  |  |  | BSS-255041000748
109 | SIGMATEC | BSS | Done Cons | WAITING PAYMENT | Planet Ban RAYA TAJEM MAGUWOHARJO | Jl. Raya Tajem No.2, RT.003/RW.031, Denokan, Maguwoharjo, Kec. Depok, Kabupaten Sleman, Daerah Istimewa Yogyakarta 55281 | https://goo.gl/maps/va mhojqZtoW3v9Ac8 | Yogyakarta | SLEMAN |  | (no WO survey) | [8 empty] | 1 |  | VGID-WO/BD/2026/IV/0533 | 2026-04-13 | 2026-04-13 | 2026-04-19 | wait VGRN |  |  |  |  | BSS-255041000763
110 | SIGMATEC | BSS | Done Cons | WAITING KWH | Planet Ban RINGROAD UTARA CONDONGCATUR | Jl. Arteri Ringroad Utara No. 03, Rt. 002, Rw. 029, Kel. Condongcatur, Kec. Depok, Kab. Sleman | https://maps.app.goo.gl/ grimnYuMqK3y6VY8A | Yogyakarta | SLEMAN |  | (no WO survey) | [8 empty] | 1 |  | VGID-WO/BD/2026/IV/0533 | 2026-04-13 | 2026-04-13 | 2026-04-18 | 2026-04-23 |  |  |  |  | BSS-255141000723
111 | SIGMATEC | BSS | On Cons | NOT YET REGISTER | Planet Ban KEBON AGUNG TLOGOADI << JALAN SINGOSARI REJOWINANGUN | ... << Jl. Singosari No. 952 B, Rt. 001, Rw. 009, Kel. Rejowinangun, Kec. Magelang Selatan, Kota Magelang | https://maps.app.goo.gl/ VwGDEcJ4fGi311da6 | Yogyakarta | SLEMAN |  | (no WO survey) | [8 empty] | 1 |  | VGID-WO/BD/2026/IV/0533 | [13 empty] | pengganti << DROP by V-Green
112 | SIGMATEC | BSS | Done Cons | NOT YET REGISTER | Planet Ban JALAN GODEAN NOGOTIRTO 2 | JL. Godean KM. 6 RT. 02 RW. 21, Kel. Nogotirto, Kec. Gamping, Kab. Sleman | https://maps.app.goo.gl/ P8mCs9M4a8UZare77 | Yogyakarta | SLEMAN |  | (no WO survey) | [8 empty] | 1 |  | VGID-WO/BD/2026/IV/0533 | 2026-04-11 | 2026-04-11 | [6 empty] | BSS-255141000551
113 | SIGMATEC | BSS | Done Cons | WAITING KWH | Planet Ban JALAN MAGELANG SINDUADI | Jl. Magelang KM 5 RT 01 RW 28, Kel. Sinduadi, Kec. Mlati, Kab. Sleman | https://maps.app.goo.gl/ 74DPjumvfuw5PQCRA | Yogyakarta | SLEMAN |  | (no WO survey) | [8 empty] | 1 |  | VGID-WO/BD/2026/IV/0533 | 2026-04-13 | 2026-04-13 | 2026-04-18 | 2026-04-23 |  |  |  |  | BSS-255141000635
114 | SIGMATEC | BSS | Done Cons | WAITING PAYMENT | Planet Ban KEBON AGUNG TRIHANGGO | Jl. Kebon Agung/Kronggahan, RT. 008, RW. 004, Kel. Trihanggo, Kec. Gamping, Kab. Sleman | https://maps.app.goo.gl/ YV1ff94uubsoraxy9 | Yogyakarta | SLEMAN |  | (no WO survey) | [8 empty] | 1 |  | VGID-WO/BD/2026/IV/0533 | 2026-04-12 | 2026-04-12 | 2026-04-15 | wait VGRN |  |  |  |  | BSS-255141000550
115 | SIGMATEC | BSS | Done Cons | WAITING KWH | Planet Ban IMOGIRI TIMUR TAMANAN | Jl. Imogiri Tim. No.35-33, Krobokan, Tamanan, Kec. Banguntapan, Kabupaten Bantul, Daerah Istimewa Yogyakarta 55191 | https://goo.gl/maps/ktL EfnqiEVFaUFGE9 | Yogyakarta | Bantul |  | (no WO survey) |  |  |  |  | New Power | 7.7kVA |  |  | 1 |  | VGID-WO/BD/2026/IV/0533 | 2026-04-13 | 2026-04-13 | 2026-04-18 | 2026-04-23 |  |  |  |  | BSS-255141000875
116 | SIGMATEC | BSS | Done Cons | NOT YET REGISTER | Planet Ban BRIGJEN KATAMSO MOJOSONGO | Jl. Brigjend Katamso No.16, Mojosongo, Kec. Jebres, Kota Surakarta, Jawa Tengah 57127 | https://goo.gl/maps/sCk 6Ncu6gcNZZdtW8 | Central Java | SURAKARTA |  | (no WO survey) | [8 empty] | 1 |  | VGID-WO/BD/2026/IV/0533 | 2026-04-19 | 2026-04-19 | [6 empty] | BSS-255141000553
117 | SIGMATEC | BSS | Done Cons | NOT YET REGISTER | Planet Ban RAYA SONGGOLANGIT GENTAN | Jl Raya Songgolangit No.1 RT 05 / RW 01. Kel. Gentan, Kec. Baki, Kec. Sukoharjo, Kabupaten Sukoharjo, Jawa Tengah 57556 | https://goo.gl/maps/S1Y 538MDJ8fMkxTc7 | Central Java | Sukoharjo |  | (no WO survey) | [8 empty] | 1 |  | VGID-WO/BD/2026/IV/0533 | 2026-04-16 | 2026-04-16 | [6 empty] | BSS-255141000780
118 | SIGMATEC | BSS | Done Cons | NOT YET REGISTER | Planet Ban TINGKIR TENGAH SALATIGA | Jl. Suruh - Karanggede, Tingkir Tengah, Kec. Tingkir, Kota Salatiga, Jawa Tengah 50745 | https://goo.gl/maps/3Bx xe7FCbBsf8tAo8 | Central Java | SALATIGA |  | (no WO survey) | [8 empty] | 1 |  | VGID-WO/BD/2026/IV/0533 | 2026-04-18 | 2026-04-18 | [6 empty] | BSS-26011541000099
119 | SIGMATEC | BSS | Done Cons | NOT YET REGISTER | Planet Ban RAYA URUTSEWU AMPEL | Jalan Raya Semarang-Boyolali Kelurahan Urutsewu Kecamatan Ampel Kabupaten Boyolali | https://maps.app.goo.gl/ nGcrES97kCjVjXfG9 | Central Java | BOYOLALI |  | (no WO survey) | [8 empty] | 1 |  | VGID-WO/BD/2026/IV/0533 | 2026-04-19 | 2026-04-19 | [6 empty] | BSS-255141000781
120 | SIGMATEC | BSS | Done Cons | NOT YET REGISTER | Planet Ban LAWU TEGALGEDE KARANGANYAR | Jl. Lawu No.127, Kel. Tegalgede Kec. Karanganyar, Kab. Karanganyar, Jawa Tengah | https://maps.app.goo.gl/ 4LHQ8NtYzEWU533e9 | Central Java | Karanganyar |  | (no WO survey) | [8 empty] | 1 |  | VGID-WO/BD/2026/IV/0533 | 2026-04-20 | 2026-04-20 | [6 empty] | BSS-255141000801
121 | SIGMATEC | BSS | Done Cons | WAITING KWH | Planet Ban JALAN PARANGTRITIS TIMBULHARJO | Jl. Parangtritis No. 8, RW. 03, Kel. Timbulharjo, Kec. Sewon, Kab. Bantul | https://maps.app.goo.gl/ yzMZMSpXRis9p4Fz8 | Yogyakarta | Bantul |  | (no WO survey) |  |  |  |  | New Power | 7.7kVA |  |  | 1 |  | VGID-WO/BD/2026/IV/0533 | 2026-04-12 | 2026-04-12 | 2026-04-15 | 2026-04-23 |  |  |  |  | BSS-255141000619
122 | SIGMATEC | BSS | Drop | NOT YET REGISTER | Planet Ban RAYA TELUKAN GROGOL | Jl. Raya Telukan No. 5B RT.01/01, Kel. Telukan, Kec. Grogol, Kab. Sukoharjo | https://goo.gl/maps/JYw p1qEJ8nHGUkLA9 | Central Java | Sukoharjo |  | (no WO survey) | [8 empty] | 1 |  | VGID-WO/BD/2026/IV/0533 | - | - | - | - |  |  |  |  | - |  |  |  |  | DROP by V-Green | -
123 | SIGMATEC | BSS | Done Cons | NOT YET REGISTER | Planet Ban JALAN DIPONEGORO WONOBOYO | jl. diponegoro no.45, kel. wonoboyo, kec. wonogiri, kab. wonogiri | https://maps.app.goo.gl/ odgMXqEukHpLAPh28 | Central Java | WONOGIRI |  | (no WO survey) | [8 empty] | 1 |  | VGID-WO/BD/2026/IV/0533 | 2026-04-20 | 2026-04-20 | [6 empty] | BSS-255141000930
124 | SIGMATEC | BSS | Done Cons | NOT YET REGISTER | Planet Ban JALAN RANDUSARIKLATEN SUDIMORO | Jl. Randusari Klaten, Kel. Sudimoro, Kec. Teras, Kab. Boyolali | https://maps.app.goo.gl/ xCcuu6nF7Gn426W76 | Central Java | BOYOLALI |  | (no WO survey) | [8 empty] | 1 |  | VGID-WO/BD/2026/IV/0533 | 2026-04-16 | 2026-04-16 | [6 empty] | BSS-255141000944
125 | SIGMATEC | BSS | Done Cons | WAITING KWH | Planet Ban RAYA CANTELAN SLARANG | Jl. Raya Cantelan, Kelurahan Slarang, Kec. Kesugihan, Kab. Cilacap | https://maps.app.goo.gl/ fPgbr9PC2N22jgF79 | Central Java | CILACAP |  | (no WO survey) | [8 empty] | 1 |  | VGID-WO/BD/2026/IV/0533 | 2026-04-17 | 2026-04-17 | 2026-04-20 | 2026-04-23 |  |  |  |  | BSS-254941002193
126 | SIGMATEC | BSS | Done Cons | NOT YET REGISTER | Planet Ban IR JUANDA PURWODININGRATAN | Jl. Ir. Juanda, Purwodiningratan, Kec. Jebres, Kota Surakarta, Jawa Tengah 57121 | https://goo.gl/maps/Sht xzpYm5birDCct8 | Central Java | SURAKARTA |  | (no WO survey) | [8 empty] | 1 |  | VGID-WO/BD/2026/IV/0533 | 2026-04-20 | 2026-04-20 | [6 empty] | BSS-255141000824 |  |  |  |  | mau di drop?
127 | SIGMATEC | BSS | Done Cons | DONE KWH | Planet Ban JALAN REVOLUSI KARANGANYAR | Jl. Revolusi no. 43, Kel. Karanganyar, Kec. Karanganyar, Kab. Kebumen | https://maps.app.goo.gl/ EBjcaKW52K82mFYh6 | Central Java | KEBUMEN |  | (no WO survey) | [8 empty] | 1 |  | VGID-WO/BD/2026/IV/0533 | 2026-04-15 | 2026-04-15 | 2026-04-18 | 2026-04-23 |  |  |  | 2026-04-29 | BSS-255141000787
128 | SIGMATEC | BSS | Done Cons | NOT YET REGISTER | Planet Ban ADI SUMARMO MALANGJIWAN | Jl. Adi Sumarmo, Kel. Malangjiwan, Kec. Colomadu, Kab. Karanganyar | https://maps.app.goo.gl/ yz9PtbYo1rYveNBs8 | Central Java | Karanganyar |  | (no WO survey) | [8 empty] | 1 |  | VGID-WO/BD/2026/IV/0533 | 2026-04-19 | 2026-04-19 | [6 empty] | BSS-255141000813
129 | SIGMATEC | BSS | Done Cons | NOT YET REGISTER | Planet Ban H MUSLICH WONOREJO | Jl. H. Muslich, RT. 02 RW 06, Kel. Wonorejo, Kec. Polokarto, Kab. Sukoharjo | https://maps.app.goo.gl/ exDv4e99c272G9Ly6 | Central Java | Sukoharjo |  | (no WO survey) | [8 empty] | 1 |  | VGID-WO/BD/2026/IV/0533 | 2026-04-18 | 2026-04-18 | [6 empty] | BSS-255141000810
130 | SIGMATEC | BSS | Done Cons | NOT YET REGISTER | Planet Ban GARUDA MAS KARANGASEM 2 | Jl. Garuda Mas No. 23, Kel. Karangasem, Kec. Lawean, Kota Surakarta | https://maps.app.goo.gl/ mR1FuqVxZorama9q7 | Central Java | SURAKARTA |  | (no WO survey) | [8 empty] | 1 |  | VGID-WO/BD/2026/IV/0533 | 2026-04-19 | 2026-04-19 | [6 empty] | BSS-255041000732
131 | SIGMATEC | BSS | Done Cons | NOT YET REGISTER | Planet Ban LETJEND SUTOYO JOGLO | Jl. Letjend Sutoyo RT.02 RW.02, Kel. Joglo Kec. Banjarsari, Kota Surakarta | https://maps.app.goo.gl/ vSzDCyBSvbB2eJVXA | Central Java | SURAKARTA |  | (no WO survey) | [8 empty] | 1 |  | VGID-WO/BD/2026/IV/0533 | 2026-04-19 | 2026-04-19 | [6 empty] | BSS-255141000667
132 | SIGMATEC | BSS | Done Cons | NOT YET REGISTER | Planet Ban JALAN PATIMURA SALATIGA | Jl. Patimura Nomor 2, RT. 002, RW. 005, Kel. Salatiga, Kec. Sidorejo, Kota Salatiga | https://goo.gl/maps/mk 49rhcLs1QfV9wC8 | Central Java | SALATIGA |  | (no WO survey) | [8 empty] | 1 |  | VGID-WO/BD/2026/IV/0533 | 2026-04-19 | 2026-04-19 | [6 empty] | BSS-26011541000084
133 | SIGMATEC | BSS | Drop | NOT YET REGISTER | Planet Ban Raya Utara Wangon II | Jl. Raya Utara No. 89, Kel. Wangon, Kec. Wangon, Kabupaten Banyumas | https://maps.app.goo.gl/ gsDmciNeK3DTWdeeA | Central Java | Banyumas |  | (no WO survey) | [8 empty] | 1 |  | VGID-WO/BD/2026/IV/0533 | - | - | - | - |  |  |  |  | - |  |  |  |  | DROP by V-Green | -
134 | SIGMATEC | BSS | Drop | NOT YET REGISTER | Planet Ban RE Martadinata Tambakreja | Jl. RE Martadinata No. 11 RT. 02 RW. 01, Kel. Tambakreja, Kec. Cilacap Selatan, Kab. Cilacap | https://maps.app.goo.gl/ LDXSEPfyYrfShf4w8 | Central Java | CILACAP |  | (no WO survey) | [8 empty] | 1 |  | VGID-WO/BD/2026/IV/0533 | - | - | - | - |  |  |  |  | - |  |  |  |  | DROP by V-Green | -
135 | SIGMATEC | BSS | Drop | NOT YET REGISTER | Planet Ban Mayjen YudomoSHD Lalung | Jl. Mayjend Yudomo SHD, RT. 03, RW. 14, Kel. Lalung, Kec. Karanganyar, Karanganyar Kab | https://maps.app.goo.gl/ 8A8QUprpZWvaX5BK7 | Central Java | Karanganyar |  | (no WO survey) | [8 empty] | 1 |  | VGID-WO/BD/2026/IV/0533 | - | - | - | - |  |  |  |  | - |  |  |  |  | DROP by V-Green | -
136 | SIGMATEC | BSS | On Cons | NOT YET REGISTER | Planet Ban LINGKARSELATAN NGOTET REMBANG |  |  | Central Java | Rembang |  | (no WO survey) | [8 empty] | 1 |  | VGID-WO/BD/2026/IV/0533 | [13 empty] | pengganti site yg DROP
137 | SIGMATEC | BSS | SS Done | NOT YET REGISTER | Hotel Timur | Jl. Gedongkuning No.142, Selatan, Rejowinangun, Kec. Kotagede, Kota Yogyakarta, Daerah Istimewa Yogyakarta 55171 | https://maps.app.goo.gl/zRhTMVHyC8wJf769A | Yogyakarta | Yogyakarta | Adi | VGID-WO/BD/2026/IV/0758 | 2026-04-21 | 2026-04-29 |  |  | New Power | 7.7kVA |  |  | 1
138 | SIGMATEC | BSS | Site Survey | NOT YET REGISTER | Erafone & More Sudirman Bantul | Jl. Jend. Sudirman No.27 B, Bantul Wr., Bantul, Kec. Bantul, Kabupaten Bantul, Daerah Istimewa Yogyakarta 55711 | https://maps.app.goo.gl/tQozQTVCisPFF3y96 | Yogyakarta | Yogyakarta | Frisca 087784164941 | VGID-WO/BD/2026/IV/0799 | [8 empty] | 1
139 | SIGMATEC | BSS | Site Survey | NOT YET REGISTER | Erafone & More Pandanaran SMG | Jl. Pandanaran No.104, Pekunden, Kec. Semarang Tengah, Kota Semarang, Jawa Tengah 50241 | https://maps.app.goo.gl/CVRnGHGi3BaUVuEe8 | Central Java | Semarang | Frisca 087784164941 | VGID-WO/BD/2026/IV/0799 | [8 empty] | 1
140 | SIGMATEC | BSS | Site Survey | NOT YET REGISTER | Erafone & More Pekalongan | Jl. Urip Sumoharjo, Medono, Kec. Pekalongan Bar., Kota Pekalongan, Jawa Tengah 51111 | https://maps.app.goo.gl/PXwZbMjimocwPE73A | Central Java | Pekalongan | Frisca 087784164941 | VGID-WO/BD/2026/IV/0799 | [8 empty] | 1
Note on AG11: 25/02/2026

## EPC Report pemasangan-EVCS
No | EPC Name | Charging Type | Project Status | PLN Status | Project / Location Name | Address | Google Map URL | Province | City | BD PIC | SS WO number | SS Date (Schedule w/ Landlord) | SS Report Submission Date | Cable Length (kWH to Panel) | Cable Length (Panel to Charger) | Cable Pulling Type | Power (Daya kVA) | SSR URL (Report & Quotation) | Parking Slot | Charging Station Count | Setup Approval Date | Cons WO number | Cons Actual Start Date | Cons Actual Done Date | NIDI SLO Date Acquired | BPUJL Date Acquired | NIDI SLO, BPUJL URL | SIK URL | Type Rate | kWh Meter PLN Installation Date | Machine SN (SERIAL NUMBER) | ID PELANGGAN (ID PLN) | NOMOR SIMCARD | Go LIVE Date (by pass) | Go LIVE Date (PLN) | Latest Remark / Notes | Tanggal Pengajuan Invoice | DP 35% Date | Tanggal Pengajuan Invoice | 60% Payment Date | Tanggal Pengajuan Invoice | 5% Payment Date | Invoice URL
1 | SIGMATEC | EVCS | On Cons | NOT YET REGISTER | Blasteran Carwash | GF33+C63, Jl. Alternative Bukit Indah – Purwakarta, Mulyamekar, Kec. Babakancikao, Kabupaten Purwakarta, Jawa Barat 41151 | https://maps.app.goo.gl/oY4QVkx5RWzxxukM6 | West Java | Purwakarta | Alfian | VGID-WO/BD/2026/II/0540 |  | 2026-03-03 |  |  | New Power | 33 KVA x2 | https://drive.google.com/drive/folders/1vmYKF_nIleGaisL8jQ4SJIhRh4Sy1aCb?usp=sharing | 2 | 2 | 2026-03-04 | VGID-WO/BD/2026/IV/0568 | 2026-04-23 | [12 empty] | bangun pondasi done, PLN reg start 29 Apr
2 | SIGMATEC | EVCS | Done Cons | WAITING BILLING | Elvano's Cafe & Photo Studio | Blok Bambo RT/RW 001/005, Kabupaten Indramayu, Jawa Barat 45264 | https://maps.app.goo.gl/EVFMnhhFFb9gH69x5 | West Java | Indramayu | Taslim | VGID-WO/BD/2026/II/0540 |  | 2026-03-03 |  |  | New Power | 23kVA | https://drive.google.com/drive/folders/1vmYKF_nIleGaisL8jQ4SJIhRh4Sy1aCb?usp=sharing | 1 | 1 | 2026-03-04 | VGID-WO/BD/2026/IV/0520 | 2026-03-31 | 2026-04-23 | [11 empty] | Cons done, PLN reg start 29 Apr | 2026-04-02
3 | SIGMATEC | EVCS | Done Cons | WAITING BILLING | RM Tahu Mekarsari | Ciherang, Kabupaten Sumedang, Jawa Barat | https://maps.app.goo.gl/5nCn1yH5Cvv3Li7a9 | West Java | Sumedang | Taslim | VGID-WO/BD/2026/II/0540 |  | 2026-03-03 |  |  | New Power | 33 KVA x2 | https://drive.google.com/drive/folders/1vmYKF_nIleGaisL8jQ4SJIhRh4Sy1aCb?usp=sharing | 2 | 2 | 2026-03-04 | VGID-WO/BD/2026/III/0495 | 2026-03-30 | 2026-04-22 | [11 empty] | Cons done, PLN reg start 29 Apr | 2026-04-01
4 | SIGMATEC | EVCS | Done Cons | WAITING KWH | Pesona Futsal | Jl. Proklamasi No.18, Jayaraga, Kec. Tarogong Kidul, Kabupaten Garut, Jawa Barat 44151 | https://maps.app.goo.gl/9Tt45V3qgbXo3uDb7 | West Java | garut | Taslim | VGID-WO/BD/2026/II/0540 |  | 2026-03-03 |  |  | New Power | 33 KVA x2 | https://drive.google.com/drive/folders/1vmYKF_nIleGaisL8jQ4SJIhRh4Sy1aCb?usp=sharing | 2 | 2 | 2026-03-04 | VGID-WO/BD/2026/III/0495 | 2026-03-30 | 2026-04-22 | 2026-03-31 | 2026-04-18 | [9 empty] | Cons done, PLN? | 2026-04-01
5 | SIGMATEC | EVCS | Done Cons | WAITING KWH | Rumah Makan Saung Wangi | Raya Tanjung Wangi–Cijambe, Gunungtua, Kec. Cijambe, Kabupaten Subang, Jawa Barat 41286 | https://maps.app.goo.gl/kE2nnxZJHMtZesfB6 | West Java | Cijambe | Taslim | VGID-WO/BD/2026/II/0522 |  | 2026-02-27 |  |  | New Power | 66kVA | https://drive.google.com/drive/folders/1f9BM2W9f4Xxw0yv10yF6RaP8iWVkcbd0?usp=sharing | 2 | 1 | 2026-02-27 | VGID-WO/BD/2026/III/0495 | 2026-03-30 | 2026-04-22 | 2026-04-03 | 2026-04-18 | [9 empty] | Cons done, PLN? | 2026-04-01
6 | SIGMATEC | EVCS | SS Done | NOT YET REGISTER | Klinik Pratama Zhafira | Jl. Maribaya No.85, Kayuambon, Kec. Lembang, Kabupaten Bandung Barat, Jawa Barat 40391 | https://maps.app.goo.gl/4wjdvb8qeHPZqXTb9 | West Java | Lembang | Taslim | VGID-WO/BD/2026/II/0522 |  | 2026-02-27 |  |  | New Power | 66kVA | https://drive.google.com/drive/folders/1f9BM2W9f4Xxw0yv10yF6RaP8iWVkcbd0?usp=sharing | 2 | 1 | 2026-02-27 | [14 empty] | menunggu WO cons
7 | SIGMATEC | EVCS | On Cons | NOT YET REGISTER | Rumah Sakit Dadi Keluarga Purwokerto | Jl. Sultan Agung No.8A, Kalibiru, Teluk, Kec. Purwokerto Selatan, Kabupaten Banyumas, Jawa Tengah 53145 | https://maps.app.goo.gl/vAPmxfhk6tokwTUT8 | Central Java | Purwokerto Selatan | Taslim | VGID-WO/BD/2026/II/0522 |  | 2026-02-27 |  |  | New Power | 23kVA | https://drive.google.com/drive/folders/1f9BM2W9f4Xxw0yv10yF6RaP8iWVkcbd0?usp=sharing | 1 | 1 | 2026-02-27 | VGID-WO/BD/2026/IV/0520 | [13 empty] | menunggu izin konstruksi dari pihak RS; RS menunggu pembayaran dari V-Green | 2026-04-02
8 | SIGMATEC | EVCS | Done Cons | WAITING KWH | Cimahi Mall | Jl. Gandawijaya, Setiamanah, Kec. Cimahi Tengah, Kota Cimahi, Jawa Barat 40524 | https://maps.app.goo.gl/ZVmeWFvpWjzcsmau6 | West Java | Cimahi Tengah | Aldi | VGID-WO/BD/2026/II/0522 |  | 2026-02-27 |  |  | New Power | 33 KVA x2 | https://drive.google.com/drive/folders/1f9BM2W9f4Xxw0yv10yF6RaP8iWVkcbd0?usp=sharing | 2 | 2 | 2026-02-27 | VGID-WO/BD/2026/III/0495 | 2026-03-30 | 2026-04-22 | 2026-04-02 | 2026-04-18 | [9 empty] | Cons done, PLN? | 2026-04-01
9 | SIGMATEC | EVCS | SS Done | NOT YET REGISTER | Apartemen Mutiara Bekasi | Jl. Ahmad Yani No.8, Pekayon Jaya, Kec. Bekasi Selatan, Kota Bekasi, Jawa Barat 17144 | https://share.google/GbIywcGaM18FbfooE | West Java | Bekasi Selatan | Raisha | VGID-WO/BD/2026/II/0522 |  | 2026-02-27 |  |  | New Power | 33 KVA x2 | https://drive.google.com/drive/folders/1f9BM2W9f4Xxw0yv10yF6RaP8iWVkcbd0?usp=sharing | 2 | 2 | 2026-02-27 | [14 empty] | menunggu WO cons
10 | SIGMATEC | EVCS | On Cons | WAITING BILLING | Jatinangor Town Square | Jl. Raya Jatinangor No.150, Cikeruh, Kec. Jatinangor, Kabupaten Sumedang, Jawa Barat 45363 | https://maps.app.goo.gl/PyGuJDpYcsgAME4F7 | West Java | Jatinangor | Alfian | VGID-WO/BD/2026/II/0522 |  | 2026-02-27 |  |  | New Power | 33kVA | https://drive.google.com/drive/folders/1f9BM2W9f4Xxw0yv10yF6RaP8iWVkcbd0?usp=sharing | 1 | 1 | 2026-02-27 | VGID-WO/BD/2026/IV/0541 | [13 empty] | potensi drop krn diminta kabel tanah << meeting BM, menunggu hasil | 2026-04-14
11 | SIGMATEC | EVCS | On Cons | NOT YET REGISTER | RM Tahu Sumedang Rasa Kedelai Cicalengka | 2RGQ+55F, National Route 3, Tenjolaya, Cicalengka, Kabupaten Bandung, Jawa Barat 40395 | https://maps.app.goo.gl/EfEuia7XJSkrzSM67 | West Java | Cicalengka | Alfian | VGID-WO/BD/2026/II/0522 |  | 2026-02-27 |  |  | New Power | 33 KVA x2 | https://drive.google.com/drive/folders/1f9BM2W9f4Xxw0yv10yF6RaP8iWVkcbd0?usp=sharing | 2 | 2 | 2026-04-22 | VGID-WO/BD/2026/IV/0588 | [13 empty] | pasang panel 30 Apr, PLN reg start 29 Apr << pondasi done, charger done
12 | SIGMATEC | EVCS | Done Cons | WAITING PAYMENT | Daop 3 Cirebon Stasiun KAI Cirebon a | Jl. Stasiun No.6, Kesenden, Kec. Kejaksan, Kota Cirebon, Jawa Barat 45122 | https://maps.app.goo.gl/fFrgT7K6MKZezXL97 | West Java | Cirebon | Genta | VGID-WO/BD/2026/III/0587 | 2026-03-16 | 2026-03-17 |  |  | New Power | 23kVA |  | 1 | 1 | 2026-04-14 | VGID-WO/BD/2026/IV/0566 | 2026-04-19 | 2026-04-24 | 2026-04-26 | wait VGRN | [9 empty] | install charger done
13 | SIGMATEC | EVCS | Done Cons | WAITING PAYMENT | Daop 3 Cirebon Stasiun KAI Cirebon b | Jl. Stasiun No.6, Kesenden, Kec. Kejaksan, Kota Cirebon, Jawa Barat 45122 | https://maps.app.goo.gl/fFrgT7K6MKZezXL97 | West Java | Cirebon | Genta | VGID-WO/BD/2026/III/0587 | 2026-03-16 | 2026-03-17 |  |  | New Power | 23kVA |  | 1 | 1 | 2026-04-14 | VGID-WO/BD/2026/IV/0566 | 2026-04-19 | 2026-04-24 | 2026-04-26 | wait VGRN | [9 empty] | install charger done
14 | SIGMATEC | EVCS | Done Cons | WAITING PAYMENT | Daop 3 Cirebon Stasiun KAI Cirebon c | Jl. Stasiun No.6, Kesenden, Kec. Kejaksan, Kota Cirebon, Jawa Barat 45122 | https://maps.app.goo.gl/fFrgT7K6MKZezXL97 | West Java | Cirebon | Genta | VGID-WO/BD/2026/III/0587 | 2026-03-16 | 2026-03-17 |  |  | New Power | 23kVA |  | 1 | 1 | 2026-04-14 | VGID-WO/BD/2026/IV/0566 | 2026-04-19 | 2026-04-24 | 2026-04-26 | wait VGRN | [9 empty] | install charger done
15 | SIGMATEC | EVCS | Done Cons | WAITING PAYMENT | Daop 3 Cirebon Stasiun KAI Cirebon d | Jl. Stasiun No.6, Kesenden, Kec. Kejaksan, Kota Cirebon, Jawa Barat 45122 | https://maps.app.goo.gl/fFrgT7K6MKZezXL97 | West Java | Cirebon | Genta | VGID-WO/BD/2026/III/0587 | 2026-03-16 | 2026-03-17 |  |  | New Power | 23kVA |  | 1 | 1 | 2026-04-14 | VGID-WO/BD/2026/IV/0566 | 2026-04-19 | 2026-04-24 | 2026-04-26 | wait VGRN | [9 empty] | install charger done
16 | SIGMATEC | EVCS | SS Done | NOT YET REGISTER | Daop 3 Cirebon Stasiun KAI Jatibarang a | Jatibarang, Kec. Jatibarang, Kabupaten Indramayu, Jawa Barat 45273 | https://maps.app.goo.gl/Dpq9vqANLkysLa3f9 | West Java | Jatibarang | Genta | VGID-WO/BD/2026/III/0587 | 2026-03-25 | 2026-03-26 |  |  | New Power | 23kVA |  | 1 | [16 empty] | menunggu WO cons
17 | SIGMATEC | EVCS | SS Done | NOT YET REGISTER | Daop 3 Cirebon Stasiun KAI Jatibarang b | Jatibarang, Kec. Jatibarang, Kabupaten Indramayu, Jawa Barat 45273 | https://maps.app.goo.gl/Dpq9vqANLkysLa3f9 | West Java | Jatibarang | Genta | VGID-WO/BD/2026/III/0587 | 2026-03-25 | 2026-03-26 |  |  | New Power | 23kVA |  | 1 | [16 empty] | menunggu WO cons
18 | SIGMATEC | EVCS | Done Cons | WAITING PAYMENT | Daop 3 Cirebon Stasiun KAI Cirebon Prujakan a | Jl. Ratu Mas Gandasari, Pekalangan, Kec. Pekalipan, Kota Cirebon, Jawa Barat 45118 | https://maps.app.goo.gl/Ǫ5oyWXMkPFEr42yE7 | West Java | Cirebon | Genta | VGID-WO/BD/2026/III/0587 | 2026-03-16 | 2026-03-17 |  |  | New Power | 23kVA |  | 1 | 1 | 2026-04-14 | VGID-WO/BD/2026/IV/0566 | 2026-04-17 | 2026-04-22 | 2026-04-26 | wait VGRN | [9 empty] | install charger done
19 | SIGMATEC | EVCS | Done Cons | WAITING PAYMENT | Daop 3 Cirebon Stasiun KAI Cirebon Prujakan b | Jl. Ratu Mas Gandasari, Pekalangan, Kec. Pekalipan, Kota Cirebon, Jawa Barat 45118 | https://maps.app.goo.gl/Ǫ5oyWXMkPFEr42yE7 | West Java | Cirebon | Genta | VGID-WO/BD/2026/III/0587 | 2026-03-16 | 2026-03-17 |  |  | New Power | 23kVA |  | 1 | 1 | 2026-04-14 | VGID-WO/BD/2026/IV/0566 | 2026-04-17 | 2026-04-22 | 2026-04-26 | wait VGRN | [9 empty] | install charger done
20 | SIGMATEC | EVCS | On Cons | NOT YET REGISTER | Daop 3 Cirebon Stasiun KAI Pegaden Baru a | wanakersa, RT.19, Kamarung, Kec. Pagaden, Kabupaten Subang, Jawa Barat 41252 | https://maps.app.goo.gl/ǪjSuZChXRerfqxfJA | West Java | Subang | Genta | VGID-WO/BD/2026/III/0587 | 2026-03-16 | 2026-03-17 |  |  | New Power | 23kVA |  | 1 | 1 | 2026-04-14 | VGID-WO/BD/2026/IV/0566 | 2026-04-28 | 2026-04-29 | [11 empty] | Cons done, PLN reg start 29 Apr
21 | SIGMATEC | EVCS | On Cons | NOT YET REGISTER | Daop 3 Cirebon Stasiun KAI Pegaden Baru b | wanakersa, RT.19, Kamarung, Kec. Pagaden, Kabupaten Subang, Jawa Barat 41252 | https://maps.app.goo.gl/ǪjSuZChXRerfqxfJA | West Java | Subang | Genta | VGID-WO/BD/2026/III/0587 | 2026-03-16 | 2026-03-17 |  |  | New Power | 23kVA |  | 1 | 1 | 2026-04-14 | VGID-WO/BD/2026/IV/0566 | 2026-04-28 | 2026-04-29 | [11 empty] | Cons done, PLN reg start 29 Apr
22 | SIGMATEC | EVCS | SS Done | NOT YET REGISTER | Terminal Non Bus Tirtomoyo | Kelurahan Tirtomoyo, Kecamatan Tirtomoyo | https://maps.app.goo.gl/jpyCSnpiAr185NiRA | Central Java | Wonogiri | Hani | VGID-WO/BD/2026/III/0594 | 2026-03-16 | 2026-03-26 |  |  | New Power | 66kVA |  | 2 | 1 | [15 empty] | menunggu WO cons
23 | SIGMATEC | EVCS | SS Done | NOT YET REGISTER | Terminal Non Bus Baturetno | Desa Baturetno, Kecamatan Baturetno | https://maps.app.goo.gl/yUkur9CHWpVcjFeD6 | Central Java | Wonogiri | Hani | VGID-WO/BD/2026/III/0594 | 2026-03-16 | 2026-03-26 |  |  | New Power | 66kVA |  | 2 | 1 | [15 empty] | menunggu WO cons
24 | SIGMATEC | EVCS | SS Done | NOT YET REGISTER | Terminal Non Bus Sidoharjo | Jarum, Ds. Kayuloko, Kec. Sidoharjo | https://maps.app.goo.gl/SqqP3MHYfMcnqrqo9 | Central Java | Wonogiri | Hani | VGID-WO/BD/2026/III/0594 | 2026-03-31 | 2026-03-31 |  |  | New Power | 66kVA |  | 2 | 1 | [15 empty] | menunggu WO cons
25 | SIGMATEC | EVCS | Drop | NOT YET REGISTER | Muesum Karst Indonesia | Mudal, Ds. Gebangharjo, Kec. Pracimantoro | https://maps.app.goo.gl/wP1yS3rFv2sNcv5C6 | Central Java | Wonogiri | Hani | VGID-WO/BD/2026/III/0594 | 2026-03-16 | 2026-03-26 |  |  |  | 33kVA |  | 1 | [16 empty] | propose drop krn tidak tersedia jaringan 3 ph di lokasi
26 | SIGMATEC | EVCS | Drop | NOT YET REGISTER | Pantai Klotok | Kawasan Pantai Paranggupito, Desa Paranggupito, Kecamatan Paranggupito | https://maps.app.goo.gl/PRYidFWBWH3ACoJ88 | Central Java | Wonogiri | Hani | VGID-WO/BD/2026/III/0594 | 2026-03-16 | 2026-03-26 |  |  |  | 33kVA |  | 1 | [16 empty] | propose drop krn tidak tersedia jaringan 3 ph di lokasi
27 | SIGMATEC | EVCS | Drop | NOT YET REGISTER | Koordinator Wilayah Pendidikan Kecamatan Ngadirojo | Dsn. Sanggrahan, Ds. Ngadirojo Kidul, Kec. Ngadirojo | https://maps.app.goo.gl/JeufXzǪTBc3gKuH66 | Central Java | Wonogiri | Hani | VGID-WO/BD/2026/III/0594 | 2026-03-16 | 2026-03-26 |  |  |  | 33kVA |  | 1 | [16 empty] | propose drop krn tidak tersedia jaringan 3 ph di lokasi
28 | SIGMATEC | EVCS | SS Done | NOT YET REGISTER | Koordinator Wilayah Pendidikan Kecamatan Girimarto | Jl. Sinuwun No. 28, Ds. Tambakmerang, Kec. Girimarto | https://maps.app.goo.gl/UV2PF9hj2zLWDwǪp8 | Central Java | Wonogiri | Hani | VGID-WO/BD/2026/III/0594 | 2026-03-16 | 2026-03-26 |  |  |  | 33kVA |  | 1 | [16 empty] | menunggu WO cons
29 | SIGMATEC | EVCS | SS Done | NOT YET REGISTER | Koordinator Wilayah Pendidikan Kecamatan Jatiroto | Jl. Raya No.37 Janggan, Kel. Jatiroto, Kec. Jatiroto | https://maps.app.goo.gl/ZLFkJR7jmotv95X1A | Central Java | Wonogiri | Hani | VGID-WO/BD/2026/III/0594 | 2026-03-16 | 2026-03-26 |  |  |  | 33kVA |  | 1 | [16 empty] | menunggu WO cons
30 | SIGMATEC | EVCS | SS Done | NOT YET REGISTER | Koordinator Wilayah Pendidikan Kecamatan Giriwoyo | Dsn. Tangkluk, Ds. Sejati, Kec. Giriwoyo | https://maps.app.goo.gl/D3tJ91aytxck9rsu8 | Central Java | Wonogiri | Hani | VGID-WO/BD/2026/III/0594 | 2026-03-16 | 2026-03-26 |  |  |  | 33kVA |  | 1 | [16 empty] | menunggu WO cons
31 | SIGMATEC | EVCS | Drop | NOT YET REGISTER | Koordinator Wilayah Pendidikan Kecamatan Eromoko | Eromoko Wetan, Ds. Eromoko, Kec. Eromoko | https://maps.app.goo.gl/RC8HYxR28y7PxkcAA | Central Java | Wonogiri | Hani | VGID-WO/BD/2026/III/0594 | 2026-03-16 | 2026-03-26 |  |  |  | 33kVA |  | 1 | [16 empty] | propose drop krn tidak tersedia jaringan 3 ph di lokasi
32 | SIGMATEC | EVCS | SS Done | NOT YET REGISTER | Kantor Kelurahan Jatikramat | Jl. H. Gemin No.2, RT.005/RW.008, Jatikramat, Kec. Jatiasih, Kota Bks, Jawa Barat 17421 | https://maps.app.goo.gl/Z3wFmSx5NSJyrKPbA | West Java | Bekasi | Raisha | VGID-WO/BD/2026/III/0624 | 2026-04-05 |  |  |  |  | 33kVA |  | 1 | [16 empty] | menunggu WO cons
33 | SIGMATEC | EVCS | SS Done | NOT YET REGISTER | Kantor Kelurahan Jatirasa | Jl. Swatantra III No.97, RT.005/RW.004, Jatirasa, Kec. Jatiasih, Kota Bks, Jawa Barat 17424 | https://maps.app.goo.gl/PHrtfKFyToaeGdRq9 | West Java | Bekasi | Raisha | VGID-WO/BD/2026/III/0624 | 2026-04-01 |  |  |  |  | 33kVA |  | 1 | [16 empty] | menunggu WO cons
34 | SIGMATEC | EVCS | Drop | NOT YET REGISTER | Puskesmas Jatimekar | Jl. Raya Kodau No.1, RT.RW 3/RW.002, Jatimekar, Kec. Jatiasih, Kota Bks, Jawa Barat 17422 | https://maps.app.goo.gl/vmǪKǪPXtHXcgxsaFA | West Java | Bekasi | Raisha | VGID-WO/BD/2026/III/0624 | 2026-04-01 |  |  |  |  | 33kVA |  | 1 | [16 empty] | propose drop krn tidak ada slot parkir
35 | SIGMATEC | EVCS | Drop | NOT YET REGISTER | Puskesmas Jatiasih | Jl. Swatantra IV No.1, RT.005/RW.004, Jatiasih, Kec. Jatiasih, Kota Bks, Jawa Barat 17423 | https://maps.app.goo.gl/sVrd4vSEiFKU8exV7 | West Java | Bekasi | Raisha | VGID-WO/BD/2026/III/0624 | 2026-04-01 |  |  |  |  | 33kVA |  | 1 | [16 empty] | propose drop krn tidak ada slot parkir
36 | SIGMATEC | EVCS | SS Done | NOT YET REGISTER | Kantor Kelurahan Jatiraden | Jl. Camar, RT.004/RW.007, Jatiraden, Kec. Jatisampurna, Kota Bks, Jawa Barat | https://maps.app.goo.gl/FryJx83FqAMcKdg67 | West Java | Bekasi | Raisha | VGID-WO/BD/2026/III/0624 | 2026-03-31 |  |  |  |  | 33kVA |  | 1 | [16 empty] | menunggu WO cons
37 | SIGMATEC | EVCS | SS Done | NOT YET REGISTER | Kantor Kelurahan Jatisampurna | Jl. H. Dehir No.39, RT.007/RW.002, Jatiluhur, Kec. Jatiasih, Kota Bks, Jawa Barat 17425, Indonesia | https://maps.app.goo.gl/TZW8BDAAraKxFy5x5 | West Java | Bekasi | Raisha | VGID-WO/BD/2026/III/0624 | 2026-03-31 |  |  |  |  | 33kVA |  | 1 | [16 empty] | menunggu WO cons
38 | SIGMATEC | EVCS | SS Done | NOT YET REGISTER | Puskesmas Jati Sampurna | Jl. Mendut, RT.003/RW.001, Jatisampurna, Kec. Jatisampurna, Kota Bks, Jawa Barat 17433 | https://maps.app.goo.gl/A7FNb1MRcSnAgUFk6 | West Java | Bekasi | Raisha | VGID-WO/BD/2026/III/0624 | 2026-04-01 |  |  |  |  | 33kVA |  | 1 | [16 empty] | menunggu WO cons
39 | SIGMATEC | EVCS | SS Done | NOT YET REGISTER | Kantor Kelurahan Harapan Mulya | QX9R+M7Q, Jl. Pangeran Jayakarta, RT.004/RW.008, Harapan Mulya, Kecamatan Medan Satria, Kota Bks, Jawa Barat 17143 | https://maps.app.goo.gl/S2q6YCKqǪMMJz9uD7 | West Java | Bekasi | Raisha | VGID-WO/BD/2026/III/0624 | 2026-03-30 |  |  |  |  | 33kVA |  | 1 | [16 empty] | menunggu WO cons
40 | SIGMATEC | EVCS | SS Done | NOT YET REGISTER | Kantor Kelurahan Medansatria | Jl. Harapan Indah Boulevard No.9B, Medan Satria, Kecamatan Medan Satria, Kota Bks, Jawa Barat 17131 | https://maps.app.goo.gl/wAJuHCTof9gk5n9B9 | West Java | Bekasi | Raisha | VGID-WO/BD/2026/III/0624 | 2026-03-30 |  |  |  |  | 33kVA |  | 1 | [16 empty] | menunggu WO cons
41 | SIGMATEC | EVCS | SS Done | NOT YET REGISTER | Puskesmas Harapan Mulya | RT.004/RW.008, Harapan Mulya, Medan Satria, Bekasi, West Java 17143 | https://maps.app.goo.gl/ǪuxsPB3Ac8uqǪs2V9 | West Java | Bekasi | Raisha | VGID-WO/BD/2026/III/0624 | 2026-03-30 |  |  |  |  | 33kVA |  | 1 | [16 empty] | menunggu WO cons
42 | SIGMATEC | EVCS | SS Done | NOT YET REGISTER | Kantor Kelurahan Cimuning | Jl. Raya Cimuning No.KM.5, RT.002/RW.001, Cimuning, Kec. Mustika Jaya, Kota Bks, Jawa Barat 17155 | https://maps.app.goo.gl/c2GNaYEw4CBRf3xi9 | West Java | Bekasi | Raisha | VGID-WO/BD/2026/III/0624 | 2026-04-16 |  |  |  |  | 33kVA |  | 1 | [16 empty] | menunggu WO cons
43 | SIGMATEC | EVCS | SS Done | NOT YET REGISTER | Kantor Kelurahan Mustikasari | Jl. Mandor Demong No.09, RT.001/RW.003, Mustikasari, Kec. Mustika Jaya, Kota Bks, Jawa Barat 17157 | https://maps.app.goo.gl/H5ghmY7es6tFos2t6 | West Java | Bekasi | Raisha | VGID-WO/BD/2026/III/0624 | 2026-04-02 |  |  |  |  | 33kVA |  | 1 | [16 empty] | menunggu WO cons
44 | SIGMATEC | EVCS | Drop | NOT YET REGISTER | Kantor Kelurahan Jatibening Baru | PWPV+R8Q, RT.013/RW.008, Jatibening Baru, Pondok Gede, Bekasi, West Java 17412 | https://maps.app.goo.gl/Kvugd1fqKYs5hqvLA | West Java | Bekasi | Raisha | VGID-WO/BD/2026/III/0624 | 2026-04-03 |  |  |  |  | 33kVA |  | 1 | [16 empty] | propose drop krn tidak ada slot parkir
45 | SIGMATEC | EVCS | SS Done | NOT YET REGISTER | Kantor Kecamatan Pondokmelati | Jl. Bulak Tinggi Raya No.77, RT.009/RW.016, Jatiwarna, Kec. Pd. Melati, Kota Bks, Jawa Barat 17415 | https://maps.app.goo.gl/VNZxdAT72ScmY85u5 | West Java | Bekasi | Raisha | VGID-WO/BD/2026/III/0624 | 2026-04-02 |  |  |  |  | 33kVA |  | 1 | [16 empty] | menunggu WO cons
46 | SIGMATEC | EVCS | SS Done | NOT YET REGISTER | Kantor Kecamatan Rawalumbu a | Jl. Raya Siliwangi No.1, RT.006/RW.001, Sepanjang Jaya, Kec. Rawalumbu, Kota Bks, Jawa Barat 17114 | https://maps.app.goo.gl/kyXuhTh7ihwL91PE9 | West Java | Bekasi | Raisha | VGID-WO/BD/2026/III/0624 | 2026-04-02 |  |  |  |  | 33kVA |  | 1 | [16 empty] | menunggu WO cons
47 | SIGMATEC | EVCS | SS Done | NOT YET REGISTER | Kantor Kecamatan Rawalumbu b | Jl. Raya Siliwangi No.1, RT.006/RW.001, Sepanjang Jaya, Kec. Rawalumbu, Kota Bks, Jawa Barat 17114 | https://maps.app.goo.gl/kyXuhTh7ihwL91PE9 | West Java | Bekasi | Raisha | VGID-WO/BD/2026/III/0624 | 2026-04-02 |  |  |  |  | 33kVA |  | 1 | [16 empty] | menunggu WO cons
48 | SIGMATEC | EVCS | SS Done | NOT YET REGISTER | Kantor Kelurahan Bojong Rawalumbu | Jl. Lumbu Tim. Raya No.1, RT.001/RW.026, Bojong Rawalumbu, Kec. Rawalumbu, Kota Bks, Jawa Barat 17114 | https://maps.app.goo.gl/j77Y6XajCjhScLnj9 | West Java | Bekasi | Raisha | VGID-WO/BD/2026/III/0624 | 2026-04-16 |  |  |  |  | 33kVA |  | 1 | [16 empty] | menunggu WO cons
49 | SIGMATEC | EVCS | SS Done | NOT YET REGISTER | Kantor Kelurahan Pengasinan | P2M6+92G, Jl. Anyelir Timur IV Bekasi, RT.004/RW.016, Pengasinan, Kec. Rawalumbu, Kota Bks, Jawa Barat 17115 | https://maps.app.goo.gl/xansB67CWR5H2XHL9 | West Java | Bekasi | Raisha | VGID-WO/BD/2026/III/0624 | 2026-04-02 |  |  |  |  | 33kVA |  | 1 | [16 empty] | menunggu WO cons
50 | SIGMATEC | EVCS | Drop | NOT YET REGISTER | Dinas Penanaman Modal dan Pelayanan Terpadu Satu Pintu (DPMPTSP) a | Komplek Pemerintahan Walikota Bekasi, Jl. Insinyur H. Juanda No.100, RT.001/RW.005, Margahayu, Kec. Bekasi Tim., Kota Bks, Jawa Barat 17144 | https://maps.app.goo.gl/1LjvcVjYHM3yrhzEA | West Java | Bekasi | Raisha | VGID-WO/BD/2026/III/0624 | 2026-04-16 |  |  |  |  | 33kVA |  | 1 | [16 empty] | propose drop krn tidak ada slot parkir
51 | SIGMATEC | EVCS | Drop | NOT YET REGISTER | Dinas Penanaman Modal dan Pelayanan Terpadu Satu Pintu (DPMPTSP) b | Komplek Pemerintahan Walikota Bekasi, Jl. Insinyur H. Juanda No.100, RT.001/RW.005, Margahayu, Kec. Bekasi Tim., Kota Bks, Jawa Barat 17144 | https://maps.app.goo.gl/1LjvcVjYHM3yrhzEA | West Java | Bekasi | Raisha | VGID-WO/BD/2026/III/0624 | 2026-04-16 |  |  |  |  | 33kVA |  | 1 | [16 empty] | propose drop krn tidak ada slot parkir
52 | SIGMATEC | EVCS | SS Done | NOT YET REGISTER | Hotel Timur | Jl. Gedongkuning No.142, Selatan, Rejowinangun, Kec. Kotagede, Kota Yogyakarta, Daerah Istimewa Yogyakarta 55171 | https://maps.app.goo.gl/zRhTMVHyC8wJf769A | Yogyakarta | Yogyakarta | Adi | VGID-WO/BD/2026/IV/0758 | 2026-04-21 | 2026-04-29 |  |  | New Power | 23kVA x2 |  | 2 | 2